## README
Portfolio Reporting - Data Template
Fill this workbook in and drop it onto the dashboard page. Every number on the dashboard is derived from these sheets.
Legend
Blue header | An INPUT column. Type your data here.
Grey header | A CALCULATED column. Contains formulas - do not overwrite.
Sample rows | Every sheet ships with realistic sample rows. Delete them and enter your own, or edit in place.
Hierarchy - how the drill-down is built
Priorities | Top level. Organisational priorities for the financial year.
Portfolios | Each links to one Priority via PriorityID.
Programs | Each links to one Portfolio via PortfolioID.
Projects | Each links to one Program via ProgramID. This is the main sheet.
Milestones / Risks / Issues / LessonsLearned | Each links to one Project via ProjectID.
The only rule that matters: every ID referenced by a child row must exist in its parent sheet. Orphan rows are reported on the dashboard's Data Health panel and excluded from rollups.
The four numbers that drive everything
BudgetAtCompletion (BAC) | Total approved budget for the project.
PlannedValue (PV) | Budgeted cost of work SCHEDULED to date.
EarnedValue (EV) | Budgeted cost of work ACTUALLY COMPLETED to date. = BAC x % complete.
ActualCost (AC) | What has actually been spent to date.
From these four, the dashboard computes SPI, CPI, variances, forecast at completion, and every RAG status. If you only ever maintain four columns, maintain these.
PMI / PMBOK formulas used
SV = EV - PV | Schedule Variance. Negative = behind schedule.
CV = EV - AC | Cost Variance. Negative = over budget.
SPI = EV / PV | Schedule Performance Index. Below 1.0 = behind schedule.
CPI = EV / AC | Cost Performance Index. Below 1.0 = over budget.
EAC = BAC / CPI | Estimate At Completion - forecast total cost at current efficiency.
VAC = BAC - EAC | Variance At Completion. Negative = forecast overrun.
Risk exposure = P x I | Probability (1-5) x Impact (1-5), giving 1-25.
RAG rules
Thresholds live on the Config sheet - change them there, never in the dashboard code. Cost RAG uses CPI, Schedule RAG uses SPI, Risk RAG uses the highest open risk exposure on the project. Overall RAG is the worst of the three.
Assumptions in the sample data
All sample rows are synthetic and generated for demonstration only. Reporting date is set on the Config sheet. Currency is USD. No figure in this workbook is drawn from a real organisation.

## Priorities
PriorityID | PriorityName | Description | ExecutiveSponsor | WeightPct | FY
PR-01 | Leading Country to build an AI-Enabled Economy | Establish sovereign AI capability end to end — compute, energy, agreements, sector deployment and urban infrastructure — and convert it into economic output. | H.E. Council Chair | 100% | FY2026

## Portfolios
PortfolioID | PortfolioName | PriorityID | PortfolioOwner | Department
PF-01 | Nationwide Foundation Layers | PR-01 | Dr. A. Al Marri | Digital Infrastructure
PF-02 | AI Compute & B2B Agreements | PR-01 | S. Ramaswamy | AI Office
PF-03 | AI Use Case Developments | PR-01 | P. Mensah | AI Office
PF-04 | AI Smart City | PR-01 | V. Petrova | Transport & Municipality

## Programs
ProgramID | ProgramName | PortfolioID | ProgramManager
PG-01 | Datacenters | PF-01 | R. Nakamura
PG-02 | G2G Contracts | PF-01 | L. Bergstrom
PG-03 | National Grids | PF-01 | K. Duarte
PG-04 | Compute Capacity & Allocation | PF-02 | T. Ivanova
PG-05 | Strategic Vendor & OEM Agreements | PF-02 | H. Lindqvist
PG-06 | Hyperscaler & Cloud Partnerships | PF-02 | J. Alvarez
PG-07 | Sovereign Model Programme | PF-02 | C. Nwosu
PG-08 | Government Services AI | PF-03 | N. Haddad
PG-09 | Healthcare AI | PF-03 | Dr. F. Rossi
PG-10 | Education & Workforce AI | PF-03 | G. Tanaka
PG-11 | Industry & Energy AI | PF-03 | R. Bhatt
PG-12 | Financial Services & RegTech AI | PF-03 | L. Moreau
PG-13 | Urban Digital Twin | PF-04 | I. Fernandes
PG-14 | Intelligent Mobility | PF-04 | M. Osei
PG-15 | Public Safety & Emergency AI | PF-04 | B. Okafor
PG-16 | Smart Utilities & Buildings | PF-04 | D. Kaur
PG-17 | Citizen Experience & Digital ID | PF-04 | E. Castellani

## Projects
ProjectID | ProjectName | ProgramID | ProjectManager | Department | Phase | Status | StartDate | BaselineFinish | ForecastFinish | PercentComplete | BudgetAtCompletion | PlannedValue | EarnedValue | ActualCost | Sponsor | BusinessCase | ScheduleVariance | CostVariance | SPI | CPI | EAC | VAC | SlipDays
PJ-001 | 200MW Tier III Facility — Thor | PG-01 | R. Nakamura | Digital Infrastructure | 4 - Monitoring & Controlling | Active | 2023-06-15 | 2027-07-10 | 2027-09-08 | 71.75% | 2064600000 | 1608887483.18 | 1481304141.29 | 1214183722.37 | Dr. A. Al Marri | Sovereign compute, energy and connectivity substrate the whole economy runs on. Delivered under Datacenters.
PJ-002 | 1GW Liquid-Cooled Facility — IronMan | PG-01 | R. Nakamura | Digital Infrastructure | 1 - Initiating | Active | 2023-12-28 | 2027-03-03 | 2027-04-01 | 9.28% | 7797000000 | 779700000 | 723924991.97 | 818966675.28 | Dr. A. Al Marri | Sovereign compute, energy and connectivity substrate the whole economy runs on. Delivered under Datacenters.
PJ-003 | 500MW Tier IV Facility — Valkyrie | PG-01 | R. Nakamura | Foreign Affairs & Trade | 2 - Planning | Active | 2024-03-19 | 2028-03-03 | 2028-03-16 | 28.18% | 2373800000 | 664664000 | 668880448.01 | 590041331.7 | Dr. A. Al Marri | Sovereign compute, energy and connectivity substrate the whole economy runs on. Delivered under Datacenters.
PJ-004 | Modular Edge DC Cluster — Sentinel (12 sites) | PG-01 | R. Nakamura | Digital Infrastructure | 2 - Planning | Active | 2025-04-18 | 2028-09-05 | 2028-10-02 | 27.27% | 267400000 | 74872000 | 72924129.15 | 64372965.05 | Dr. A. Al Marri | Sovereign compute, energy and connectivity substrate the whole economy runs on. Delivered under Datacenters.
PJ-005 | Subsea Cable Landing & DC Interconnect — Poseidon | PG-01 | R. Nakamura | Energy & Utilities | 1 - Initiating | Active | 2025-09-04 | 2027-07-14 | 2027-07-31 | 9.2% | 173400000 | 17340000 | 15960650.75 | 16468064.28 | Dr. A. Al Marri | Sovereign compute, energy and connectivity substrate the whole economy runs on. Delivered under Datacenters.
PJ-006 | Sovereign Cloud Region — Asgard | PG-01 | R. Nakamura | Digital Infrastructure | 1 - Initiating | Active | 2025-08-10 | 2026-10-23 | 2026-10-30 | 11.23% | 270200000 | 27020000 | 30335157.04 | 27455368.32 | Dr. A. Al Marri | Sovereign compute, energy and connectivity substrate the whole economy runs on. Delivered under Datacenters.
PJ-007 | GPU Supply Agreements — USA, India, UK | PG-02 | L. Bergstrom | Foreign Affairs & Trade | 3 - Executing | Active | 2026-01-29 | 2027-03-19 | 2027-04-14 | 43.03% | 8722900000 | 4192891545.89 | 3753773014.41 | 3578547054.82 | Dr. A. Al Marri | Sovereign compute, energy and connectivity substrate the whole economy runs on. Delivered under G2G Contracts.
PJ-008 | Cross-Continent Connectivity — EU, NA, India | PG-02 | L. Bergstrom | Foreign Affairs & Trade | 4 - Monitoring & Controlling | Active | 2025-11-10 | 2026-11-08 | 2026-11-19 | 66.64% | 1483800000 | 1140441322.31 | 988757748.27 | 1226911442.82 | Dr. A. Al Marri | Sovereign compute, energy and connectivity substrate the whole economy runs on. Delivered under G2G Contracts.
PJ-009 | Export Control & Chip Compliance Framework | PG-02 | L. Bergstrom | Foreign Affairs & Trade | 5 - Closing | Active | 2025-11-19 | 2026-11-11 | 2026-11-12 | 90% | 71400000 | 66402000 | 64260000 | 52672131.15 | Dr. A. Al Marri | Sovereign compute, energy and connectivity substrate the whole economy runs on. Delivered under G2G Contracts.
PJ-010 | Bilateral AI Talent Mobility Accord | PG-02 | L. Bergstrom | Energy & Utilities | 0 - Requested | On Hold | 2026-05-13 | 2027-08-22 | 2027-09-20 | 0% | 15700000 | 0 | 0 | 0 | Dr. A. Al Marri | Sovereign compute, energy and connectivity substrate the whole economy runs on. Delivered under G2G Contracts.
PJ-011 | Joint Sovereign AI Research Pact — Korea, Japan | PG-02 | L. Bergstrom | Foreign Affairs & Trade | 4 - Monitoring & Controlling | Active | 2026-05-14 | 2026-12-21 | 2027-01-12 | 42.74% | 133000000 | 56570135.75 | 56847395.48 | 49201196.35 | Dr. A. Al Marri | Sovereign compute, energy and connectivity substrate the whole economy runs on. Delivered under G2G Contracts.
PJ-012 | Cross-Border Data Adequacy Agreements | PG-02 | L. Bergstrom | AI Office | 3 - Executing | Active | 2026-02-17 | 2027-01-12 | 2027-01-27 | 49.1% | 12400000 | 6784194.53 | 6088738.02 | 7784683.72 | Dr. A. Al Marri | Sovereign compute, energy and connectivity substrate the whole economy runs on. Delivered under G2G Contracts.
PJ-013 | 4 Freezone AI Campuses Across Country | PG-03 | K. Duarte | Energy & Utilities | 4 - Monitoring & Controlling | Active | 2025-11-14 | 2028-04-13 | 2028-07-30 | 20.59% | 4413800000 | 1377746878.55 | 908651570.08 | 775360461.72 | Dr. A. Al Marri | Sovereign compute, energy and connectivity substrate the whole economy runs on. Delivered under National Grids.
PJ-014 | Powergrid Upgrade — Site A and Site B | PG-03 | K. Duarte | Energy & Utilities | 5 - Closing | Closed | 2023-09-22 | 2027-01-28 | 2027-05-18 | 90% | 1410200000 | 1311486000 | 1269180000 | 1334182668.62 | Dr. A. Al Marri | Sovereign compute, energy and connectivity substrate the whole economy runs on. Delivered under National Grids.
PJ-015 | 3GW Solar + Storage for Compute Load | PG-03 | K. Duarte | Energy & Utilities | 1 - Initiating | Active | 2026-01-13 | 2029-03-06 | 2029-03-24 | 12% | 5901500000 | 590150000 | 708180000 | 646489417.03 | Dr. A. Al Marri | Sovereign compute, energy and connectivity substrate the whole economy runs on. Delivered under National Grids.
PJ-016 | SMR Feasibility for Compute Baseload | PG-03 | K. Duarte | Energy & Utilities | 1 - Initiating | Active | 2023-07-24 | 2026-10-27 | 2026-10-29 | 10.48% | 649800000 | 64980000 | 68095811.61 | 69817317 | Dr. A. Al Marri | Sovereign compute, energy and connectivity substrate the whole economy runs on. Delivered under National Grids.
PJ-017 | National Fibre Backbone Ring | PG-03 | K. Duarte | Energy & Utilities | 3 - Executing | Active | 2024-03-25 | 2027-01-26 | 2027-02-07 | 95% | 150000000 | 126422372.23 | 142504348.75 | 143697858.43 | Dr. A. Al Marri | Sovereign compute, energy and connectivity substrate the whole economy runs on. Delivered under National Grids.
PJ-018 | Grid Interconnect & Substation Programme | PG-03 | K. Duarte | Transport & Municipality | 3 - Executing | Active | 2026-02-10 | 2028-04-14 | 2028-04-21 | 25.07% | 421300000 | 99223047.86 | 105633646.47 | 105884159.82 | Dr. A. Al Marri | Sovereign compute, energy and connectivity substrate the whole economy runs on. Delivered under National Grids.
PJ-019 | National Compute Exchange Platform | PG-04 | T. Ivanova | AI Office | 2 - Planning | Active | 2024-10-05 | 2026-07-13 | 2026-07-13 | 28.8% | 328600000 | 92008000 | 94633470.66 | 104492745.74 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Compute Capacity & Allocation.
PJ-020 | GPU-as-a-Service Commercial Launch | PG-04 | T. Ivanova | AI Office | 0 - Requested | Active | 2026-06-10 | 2028-11-19 | 2028-11-12 | 0% | 130000000 | 0 | 0 | 0 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Compute Capacity & Allocation.
PJ-021 | Compute Credits Scheme for SMEs & Startups | PG-04 | T. Ivanova | AI Office | 1 - Initiating | Active | 2025-07-10 | 2026-07-05 | 2026-07-19 | 9.24% | 76700000 | 7670000 | 7084875.69 | 7351404.8 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Compute Capacity & Allocation.
PJ-022 | Research Compute Allocation Framework | PG-04 | T. Ivanova | AI Office | 0 - Requested | Active | 2026-06-06 | 2027-03-03 | 2027-03-04 | 0% | 7400000 | 0 | 0 | 0 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Compute Capacity & Allocation.
PJ-023 | Utilisation, Metering & Chargeback System | PG-04 | T. Ivanova | Energy & Utilities | 3 - Executing | Active | 2025-05-17 | 2026-10-22 | 2026-11-02 | 95.37% | 115400000 | 100616443.59 | 110059742.17 | 106529461.82 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Compute Capacity & Allocation.
PJ-024 | Multi-Year Accelerator Framework — Tier 1 OEM | PG-05 | H. Lindqvist | Finance & Economy | 3 - Executing | Active | 2025-12-13 | 2027-08-14 | 2027-09-10 | 38.55% | 4139200000 | 1671992118.23 | 1595518263.03 | 1526215514.78 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Strategic Vendor & OEM Agreements.
PJ-025 | Second-Source Accelerator Agreement | PG-05 | H. Lindqvist | Finance & Economy | 1 - Initiating | Active | 2025-10-12 | 2027-01-09 | 2027-02-08 | 9.57% | 2165600000 | 216560000 | 207160010.6 | 221527491.27 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Strategic Vendor & OEM Agreements.
PJ-026 | Networking & Interconnect Supply Agreement | PG-05 | H. Lindqvist | Finance & Economy | 3 - Executing | Active | 2025-06-30 | 2027-04-15 | 2027-05-07 | 75.6% | 661600000 | 416787767.58 | 500145321.1 | 457352632.22 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Strategic Vendor & OEM Agreements.
PJ-027 | Liquid Cooling OEM Partnership | PG-05 | H. Lindqvist | Finance & Economy | 0 - Requested | Active | 2026-06-18 | 2027-06-26 | 2027-07-14 | 0% | 129100000 | 0 | 0 | 0 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Strategic Vendor & OEM Agreements.
PJ-028 | Semiconductor Assembly & Test Joint Venture | PG-05 | H. Lindqvist | Finance & Economy | 0 - Requested | Active | 2026-04-01 | 2027-09-03 | 2027-09-13 | 0% | 2212900000 | 0 | 0 | 0 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Strategic Vendor & OEM Agreements.
PJ-029 | Hardware Maintenance & Spares Framework | PG-05 | H. Lindqvist | Finance & Economy | 0 - Requested | Active | 2026-05-05 | 2026-11-25 | 2026-12-14 | 0% | 103400000 | 0 | 0 | 0 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Strategic Vendor & OEM Agreements.
PJ-030 | Hyperscaler Region Landing — Partner A | PG-06 | J. Alvarez | Interior & Safety | 5 - Closing | On Hold | 2025-05-26 | 2026-12-07 | 2026-12-28 | 95.29% | 2544400000 | 2366292000 | 2424525790.06 | 2941765941.42 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Hyperscaler & Cloud Partnerships.
PJ-031 | Sovereign Cloud Joint Venture | PG-06 | J. Alvarez | Digital Infrastructure | 0 - Requested | Active | 2026-06-25 | 2027-01-05 | 2027-01-12 | 0% | 534500000 | 0 | 0 | 0 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Hyperscaler & Cloud Partnerships.
PJ-032 | Enterprise Migration Incentive Programme | PG-06 | J. Alvarez | Digital Infrastructure | 0 - Requested | Active | 2026-05-27 | 2027-10-28 | 2027-11-05 | 0% | 44800000 | 0 | 0 | 0 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Hyperscaler & Cloud Partnerships.
PJ-033 | Cross-Border Compute Reciprocity Agreements | PG-06 | J. Alvarez | Digital Infrastructure | 0 - Requested | Active | 2026-07-05 | 2027-02-18 | 2027-02-18 | 0% | 97500000 | 0 | 0 | 0 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Hyperscaler & Cloud Partnerships.
PJ-034 | National Foundation Model — Training Run 1 | PG-07 | C. Nwosu | AI Office | 4 - Monitoring & Controlling | Active | 2025-10-11 | 2026-10-03 | 2026-10-22 | 80.28% | 1374900000 | 1190039495.8 | 1103827911.05 | 940379355.4 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Sovereign Model Programme.
PJ-035 | Sovereign Language Multimodal Model | PG-07 | C. Nwosu | AI Office | 1 - Initiating | Active | 2024-03-21 | 2026-08-23 | 2026-09-21 | 9.39% | 198500000 | 19850000 | 18639736.75 | 19072327.3 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Sovereign Model Programme.
PJ-036 | Model Evaluation & Red-Team Facility | PG-07 | C. Nwosu | Interior & Safety | 2 - Planning | Active | 2025-09-07 | 2027-01-02 | 2027-02-26 | 22.48% | 81700000 | 22876000 | 18367906.31 | 23023057.07 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Sovereign Model Programme.
PJ-037 | Open Model Weights Release Programme | PG-07 | C. Nwosu | Foreign Affairs & Trade | 3 - Executing | Active | 2025-12-06 | 2027-04-23 | 2027-06-04 | 45.5% | 17200000 | 8651292.25 | 7826784.2 | 8508380.59 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Sovereign Model Programme.
PJ-038 | Inference Optimisation & Serving Stack | PG-07 | C. Nwosu | AI Office | 2 - Planning | Active | 2026-05-30 | 2028-09-07 | 2028-11-28 | 7.69% | 55200000 | 5181227.44 | 4243240.14 | 4225253.36 | S. Ramaswamy | Turn installed capacity into a traded, commercially governed national asset. Delivered under Sovereign Model Programme.
PJ-039 | Citizen Services Copilot | PG-08 | N. Haddad | Health & Education | 1 - Initiating | Active | 2026-04-22 | 2026-12-22 | 2027-01-04 | 10.68% | 383200000 | 38320000 | 40922979.01 | 48458538.05 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Government Services AI.
PJ-040 | Automated Permits & Licensing | PG-08 | N. Haddad | Finance & Economy | 0 - Requested | Active | 2026-07-07 | 2027-08-08 | 2027-09-14 | 0% | 83700000 | 0 | 0 | 0 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Government Services AI.
PJ-041 | Immigration & Border AI Screening | PG-08 | N. Haddad | Health & Education | 2 - Planning | Active | 2025-11-20 | 2027-01-18 | 2027-01-22 | 28.24% | 461700000 | 129276000 | 130393153.87 | 135397358.55 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Government Services AI.
PJ-042 | Court Case Triage & Legal Research Assistant | PG-08 | N. Haddad | Interior & Safety | 3 - Executing | Active | 2025-11-29 | 2026-07-25 | 2026-08-27 | 79.68% | 65000000 | 65000000 | 51793406.01 | 53122330.79 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Government Services AI.
PJ-043 | National Document Intelligence Platform | PG-08 | N. Haddad | AI Office | 2 - Planning | Active | 2025-07-02 | 2026-06-25 | 2026-07-16 | 33.6% | 125500000 | 35140000 | 42168000 | 42557348.32 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Government Services AI.
PJ-044 | Procurement Fraud Detection | PG-08 | N. Haddad | AI Office | 3 - Executing | Active | 2025-06-26 | 2026-12-03 | 2027-01-01 | 75.96% | 11600000 | 9191619.05 | 8811496.49 | 10684604.47 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Government Services AI.
PJ-045 | Radiology Triage Deployment — 14 Hospitals | PG-09 | Dr. F. Rossi | Health & Education | 2 - Planning | Active | 2025-12-05 | 2026-08-26 | 2026-08-27 | 29.87% | 111400000 | 31192000 | 33274796.45 | 34116941.11 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Healthcare AI.
PJ-046 | National Genomics AI Platform | PG-09 | Dr. F. Rossi | Health & Education | 4 - Monitoring & Controlling | Active | 2025-10-22 | 2027-01-15 | 2027-01-08 | 71.78% | 551800000 | 365414222.22 | 396057752.67 | 344747860.72 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Healthcare AI.
PJ-047 | Predictive Bed & Capacity Management | PG-09 | Dr. F. Rossi | Health & Education | 3 - Executing | Active | 2026-06-23 | 2027-02-23 | 2027-02-16 | 23.76% | 18200000 | 4011428.57 | 4324298.81 | 3847045.29 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Healthcare AI.
PJ-048 | Clinical Documentation Assistant | PG-09 | Dr. F. Rossi | Health & Education | 1 - Initiating | Active | 2026-04-27 | 2027-02-11 | 2027-03-07 | 8.85% | 30700000 | 3070000 | 2717060.41 | 3102618.24 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Healthcare AI.
PJ-049 | Population Health Risk Stratification | PG-09 | Dr. F. Rossi | Health & Education | 1 - Initiating | Active | 2026-05-05 | 2026-10-23 | 2026-11-21 | 8.99% | 23700000 | 2370000 | 2130205.01 | 2104610.96 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Healthcare AI.
PJ-050 | AI Literacy Curriculum — National K-12 Rollout | PG-10 | G. Tanaka | Finance & Economy | 3 - Executing | Active | 2025-05-26 | 2026-10-24 | 2026-11-06 | 92.54% | 302700000 | 262222674.42 | 280107857.3 | 276332511.09 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Education & Workforce AI.
PJ-051 | 100k AI Practitioner Reskilling Programme | PG-10 | G. Tanaka | Transport & Municipality | 3 - Executing | Active | 2026-01-04 | 2027-04-10 | 2027-04-07 | 55.42% | 774800000 | 376475488.07 | 429390450.51 | 435035020.98 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Education & Workforce AI.
PJ-052 | University AI Research Chairs | PG-10 | G. Tanaka | Health & Education | 0 - Requested | Active | 2026-06-03 | 2027-10-09 | 2027-10-25 | 0% | 137800000 | 0 | 0 | 0 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Education & Workforce AI.
PJ-053 | Adaptive Learning Platform Pilot | PG-10 | G. Tanaka | Health & Education | 4 - Monitoring & Controlling | Active | 2025-09-03 | 2027-01-17 | 2027-02-13 | 58.86% | 16600000 | 11497405.19 | 9771466.1 | 11784852.52 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Education & Workforce AI.
PJ-054 | National AI Certification Framework | PG-10 | G. Tanaka | Health & Education | 4 - Monitoring & Controlling | Active | 2025-06-28 | 2026-11-04 | 2026-11-15 | 78.42% | 6400000 | 5363562.75 | 5018906.65 | 5002287.71 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Education & Workforce AI.
PJ-055 | Predictive Maintenance — National Refineries | PG-11 | R. Bhatt | Energy & Utilities | 4 - Monitoring & Controlling | Active | 2026-01-02 | 2027-03-06 | 2027-03-30 | 52.37% | 117300000 | 61938785.05 | 61429540.86 | 57802757.9 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Industry & Energy AI.
PJ-056 | Grid Load Forecasting & Optimisation | PG-11 | R. Bhatt | Energy & Utilities | 1 - Initiating | Active | 2025-12-03 | 2027-05-16 | 2027-06-03 | 11.27% | 49100000 | 4910000 | 5535795.93 | 4805049.95 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Industry & Energy AI.
PJ-057 | Port & Logistics Optimisation | PG-11 | R. Bhatt | Energy & Utilities | 5 - Closing | Active | 2025-10-29 | 2027-05-09 | 2027-05-27 | 94.98% | 114600000 | 106578000 | 108851474.91 | 116096639.2 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Industry & Energy AI.
PJ-058 | Water Network Leak Detection | PG-11 | R. Bhatt | Interior & Safety | 3 - Executing | Active | 2026-03-17 | 2027-06-03 | 2027-07-03 | 28.86% | 22300000 | 7651467.27 | 6435952.74 | 6652915.53 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Industry & Energy AI.
PJ-059 | Agricultural Yield Optimisation | PG-11 | R. Bhatt | Finance & Economy | 2 - Planning | Active | 2025-12-05 | 2026-08-24 | 2026-08-26 | 27.57% | 23400000 | 6552000 | 6451380.93 | 7146092.4 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Industry & Energy AI.
PJ-060 | AML Transaction Monitoring Uplift | PG-12 | L. Moreau | Finance & Economy | 5 - Closing | Closed | 2026-03-18 | 2026-12-02 | 2026-12-07 | 92.84% | 36500000 | 33945000 | 33887879.54 | 34945350.11 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Financial Services & RegTech AI.
PJ-061 | Real-Time Payments Fraud Engine | PG-12 | L. Moreau | Finance & Economy | 3 - Executing | Active | 2025-04-11 | 2026-12-15 | 2026-12-15 | 79.39% | 50300000 | 40371288.74 | 39935575.7 | 38624629.37 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Financial Services & RegTech AI.
PJ-062 | Regulatory Reporting Automation | PG-12 | L. Moreau | Interior & Safety | 1 - Initiating | Active | 2025-10-11 | 2026-06-15 | 2026-07-07 | 8.64% | 16100000 | 1610000 | 1390374.93 | 1566710.12 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Financial Services & RegTech AI.
PJ-063 | Credit Decisioning for Thin-File Segments | PG-12 | L. Moreau | Finance & Economy | 4 - Monitoring & Controlling | Active | 2026-01-27 | 2027-05-28 | 2027-05-18 | 43.94% | 20800000 | 8602469.14 | 9138728 | 11268934.88 | P. Mensah | Convert capability into measurable outcomes, sector by sector. Delivered under Financial Services & RegTech AI.
PJ-064 | City-Scale 3D Digital Twin — Phase 1 | PG-13 | I. Fernandes | Transport & Municipality | 2 - Planning | Active | 2026-02-25 | 2028-04-02 | 2028-06-25 | 17.42% | 208800000 | 46823468.06 | 36382650.31 | 33532174.28 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Urban Digital Twin.
PJ-065 | Real-Time Sensor Mesh Deployment | PG-13 | I. Fernandes | Transport & Municipality | 2 - Planning | Active | 2025-09-19 | 2029-07-09 | 2029-07-07 | 25.67% | 74900000 | 17848740.1 | 19230270.43 | 19567595.9 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Urban Digital Twin.
PJ-066 | Urban Planning Simulation Engine | PG-13 | I. Fernandes | Transport & Municipality | 1 - Initiating | Active | 2025-06-08 | 2027-09-28 | 2027-10-14 | 12% | 77500000 | 7750000 | 9300000 | 11037852.06 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Urban Digital Twin.
PJ-067 | Construction Progress Monitoring AI | PG-13 | I. Fernandes | Transport & Municipality | 4 - Monitoring & Controlling | Active | 2026-01-23 | 2027-03-11 | 2027-04-28 | 40.22% | 3400000 | 1691747.57 | 1367453.39 | 1407105.02 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Urban Digital Twin.
PJ-068 | Adaptive Traffic Signal Network | PG-14 | M. Osei | Finance & Economy | 1 - Initiating | Active | 2025-01-08 | 2028-03-12 | 2028-05-29 | 8.48% | 467500000 | 46750000 | 39644966.12 | 39010506.88 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Intelligent Mobility.
PJ-069 | Autonomous Shuttle Pilot — District 1 | PG-14 | M. Osei | Transport & Municipality | 2 - Planning | Active | 2025-12-23 | 2027-04-14 | 2027-04-21 | 29.87% | 107900000 | 30212000 | 32226923.56 | 33532439.34 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Intelligent Mobility.
PJ-070 | Multimodal Transit Demand Prediction | PG-14 | M. Osei | Transport & Municipality | 1 - Initiating | Active | 2025-08-11 | 2026-08-18 | 2026-08-15 | 10.14% | 3500000 | 350000 | 354958.05 | 396736.65 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Intelligent Mobility.
PJ-071 | Smart Parking & Curb Management | PG-14 | M. Osei | Transport & Municipality | 4 - Monitoring & Controlling | Active | 2025-08-11 | 2027-01-09 | 2027-02-15 | 58.4% | 8900000 | 6381782.95 | 5197348.29 | 4394904.31 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Intelligent Mobility.
PJ-072 | EV Charging Network Optimisation | PG-14 | M. Osei | Transport & Municipality | 0 - Requested | Active | 2026-03-23 | 2029-10-30 | 2029-10-24 | 0% | 63000000 | 0 | 0 | 0 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Intelligent Mobility.
PJ-073 | Emergency Response Dispatch AI | PG-15 | B. Okafor | Finance & Economy | 5 - Closing | Active | 2026-04-27 | 2027-04-17 | 2027-05-11 | 100% | 110600000 | 102858000 | 110600000 | 94748552.87 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Public Safety & Emergency AI.
PJ-074 | Flood & Heat Early Warning System | PG-15 | B. Okafor | Interior & Safety | 0 - Requested | Active | 2026-07-26 | 2027-11-26 | 2027-12-14 | 0% | 138700000 | 0 | 0 | 0 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Public Safety & Emergency AI.
PJ-075 | Crowd Density Monitoring — Major Venues | PG-15 | B. Okafor | Interior & Safety | 4 - Monitoring & Controlling | On Hold | 2026-02-28 | 2027-04-23 | 2027-04-13 | 43.87% | 3400000 | 1371360.38 | 1491580.76 | 1485951.15 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Public Safety & Emergency AI.
PJ-076 | Video Analytics Privacy & Governance Framework | PG-15 | B. Okafor | Interior & Safety | 0 - Requested | Active | 2026-05-25 | 2027-08-12 | 2027-08-04 | 0% | 24800000 | 0 | 0 | 0 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Public Safety & Emergency AI.
PJ-077 | Smart Metering Rollout — 1.2M Premises | PG-16 | D. Kaur | Energy & Utilities | 5 - Closing | Active | 2025-11-03 | 2028-11-17 | 2028-11-12 | 97% | 832400000 | 774132000 | 807438550.7 | 764460544.09 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Smart Utilities & Buildings.
PJ-078 | District Cooling Optimisation | PG-16 | D. Kaur | Energy & Utilities | 3 - Executing | Active | 2026-01-17 | 2027-01-06 | 2027-01-04 | 67.05% | 125500000 | 74803672.32 | 84152029.39 | 78957623.42 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Smart Utilities & Buildings.
PJ-079 | Building Energy Management AI | PG-16 | D. Kaur | Energy & Utilities | 0 - Requested | Active | 2026-07-19 | 2027-04-22 | 2027-05-19 | 0% | 111400000 | 0 | 0 | 0 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Smart Utilities & Buildings.
PJ-080 | Waste Collection Route Optimisation | PG-16 | D. Kaur | Energy & Utilities | 1 - Initiating | Active | 2026-01-12 | 2027-01-09 | 2027-01-28 | 9.89% | 17500000 | 1750000 | 1730133.32 | 1857160.54 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Smart Utilities & Buildings.
PJ-081 | Unified Digital Identity Wallet | PG-17 | E. Castellani | Interior & Safety | 3 - Executing | Active | 2025-10-09 | 2026-12-30 | 2027-01-08 | 69.44% | 340200000 | 236693959.73 | 236248862.15 | 224492955.49 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Citizen Experience & Digital ID.
PJ-082 | Single Citizen Portal Consolidation | PG-17 | E. Castellani | Interior & Safety | 0 - Requested | Active | 2026-05-21 | 2026-10-25 | 2026-11-04 | 0% | 26700000 | 0 | 0 | 0 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Citizen Experience & Digital ID.
PJ-083 | Multilingual Citizen Assistant | PG-17 | E. Castellani | Transport & Municipality | 2 - Planning | Active | 2025-07-09 | 2026-12-19 | 2027-01-25 | 22.52% | 96300000 | 26964000 | 21683503.88 | 18796671.07 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Citizen Experience & Digital ID.
PJ-084 | Accessibility & Inclusion Programme | PG-17 | E. Castellani | Interior & Safety | 2 - Planning | Active | 2025-12-15 | 2027-06-25 | 2027-08-16 | 24.39% | 15400000 | 4312000 | 3756784.85 | 4003330.53 | V. Petrova | Land the capability in the physical city — mobility, safety, utilities, identity. Delivered under Citizen Experience & Digital ID.
Formulas:
SlipDays = IFERROR(DATEDIF([BaselineFinish],[ForecastFinish],"d"),0)

## Milestones
MilestoneID | ProjectID | MilestoneName | BaselineDate | ForecastDate | ActualDate | Status
MS-0001 | PJ-001 | Land & Permits Secured | 2024-01-13 | 2024-01-14 | 2024-01-14 | Complete
MS-0002 | PJ-001 | Design Authority Approval | 2024-08-12 | 2024-09-23 | 2024-09-23 | Complete
MS-0003 | PJ-001 | Power Energisation | 2025-03-12 | 2025-04-19 |  | Overdue
MS-0004 | PJ-001 | Equipment Installation Complete | 2025-10-11 | 2025-11-26 | 2025-11-26 | Complete
MS-0005 | PJ-001 | Commissioning & Test | 2026-05-11 | 2026-05-07 | 2026-05-07 | Complete
MS-0006 | PJ-001 | Operational Handover | 2026-12-09 | 2026-12-07 |  | Planned
MS-0007 | PJ-002 | Site Selection Approved | 2024-05-21 | 2024-05-20 | 2024-05-20 | Complete
MS-0008 | PJ-002 | Grid Connection Agreement | 2024-10-13 | 2024-11-28 | 2024-11-28 | Complete
MS-0009 | PJ-002 | Construction Start | 2025-03-07 | 2025-03-12 | 2025-03-12 | Complete
MS-0010 | PJ-002 | Power Energisation | 2025-07-30 | 2025-09-14 | 2025-09-14 | Complete
MS-0011 | PJ-002 | Equipment Installation Complete | 2025-12-22 | 2025-12-27 | 2025-12-27 | Complete
MS-0012 | PJ-002 | Commissioning & Test | 2026-05-16 | 2026-06-20 | 2026-06-20 | Complete
MS-0013 | PJ-002 | Operational Handover | 2026-10-08 | 2026-10-18 |  | Planned
MS-0014 | PJ-003 | Site Selection Approved | 2024-10-11 | 2024-10-15 |  | Overdue
MS-0015 | PJ-003 | Land & Permits Secured | 2025-05-05 | 2025-05-11 | 2025-05-11 | Complete
MS-0016 | PJ-003 | Grid Connection Agreement | 2025-11-28 | 2025-11-22 | 2025-11-22 | Complete
MS-0017 | PJ-003 | Design Authority Approval | 2026-06-22 | 2026-07-08 | 2026-07-08 | Complete
MS-0018 | PJ-003 | Construction Start | 2027-01-15 | 2027-01-11 |  | Planned
MS-0019 | PJ-003 | Power Energisation | 2027-08-09 | 2027-08-04 |  | Planned
MS-0020 | PJ-004 | Site Selection Approved | 2025-09-19 | 2025-09-29 | 2025-09-29 | Complete
MS-0021 | PJ-004 | Land & Permits Secured | 2026-02-21 | 2026-02-23 | 2026-02-23 | Complete
MS-0022 | PJ-004 | Design Authority Approval | 2026-07-25 | 2026-08-19 |  | Planned
MS-0023 | PJ-004 | Construction Start | 2026-12-27 | 2027-01-08 |  | Planned
MS-0024 | PJ-004 | Power Energisation | 2027-05-30 | 2027-05-30 |  | Planned
MS-0025 | PJ-004 | Equipment Installation Complete | 2027-11-01 | 2027-11-05 |  | Planned
MS-0026 | PJ-004 | Commissioning & Test | 2028-04-03 | 2028-04-09 |  | Planned
MS-0027 | PJ-005 | Site Selection Approved | 2025-11-27 | 2025-12-11 | 2025-12-11 | Complete
MS-0028 | PJ-005 | Land & Permits Secured | 2026-02-20 | 2026-03-16 | 2026-03-16 | Complete
MS-0029 | PJ-005 | Grid Connection Agreement | 2026-05-16 | 2026-06-19 | 2026-06-19 | Complete
MS-0030 | PJ-005 | Design Authority Approval | 2026-08-09 | 2026-08-12 | 2026-08-12 | Complete
MS-0031 | PJ-005 | Equipment Installation Complete | 2026-11-01 | 2026-11-13 |  | Planned
MS-0032 | PJ-005 | Commissioning & Test | 2027-01-25 | 2027-01-30 |  | Planned
MS-0033 | PJ-005 | Operational Handover | 2027-04-20 | 2027-04-30 |  | Planned
MS-0034 | PJ-006 | Architecture Baselined | 2025-11-05 | 2025-11-01 | 2025-11-01 | Complete
MS-0035 | PJ-006 | Environment Provisioned | 2026-02-01 | 2026-02-16 | 2026-02-16 | Complete
MS-0036 | PJ-006 | Production Go-Live | 2026-04-30 | 2026-04-26 | 2026-04-26 | Complete
MS-0037 | PJ-006 | Benefits Review | 2026-07-27 | 2026-07-25 |  | Overdue
MS-0038 | PJ-007 | Counterpart Engagement Opened | 2026-03-29 | 2026-03-31 | 2026-03-31 | Complete
MS-0039 | PJ-007 | Legal & Compliance Review | 2026-05-27 | 2026-06-25 | 2026-06-25 | Complete
MS-0040 | PJ-007 | Cabinet / Board Approval | 2026-07-25 | 2026-08-07 | 2026-08-07 | Complete
MS-0041 | PJ-007 | Signature | 2026-09-22 | 2026-10-09 |  | Planned
MS-0042 | PJ-007 | Ratification Complete | 2026-11-20 | 2026-11-26 |  | Planned
MS-0043 | PJ-007 | First Delivery Received | 2027-01-18 | 2027-02-05 |  | Planned
MS-0044 | PJ-008 | Mandate Approved | 2025-12-31 | 2026-01-26 | 2026-01-26 | Complete
MS-0045 | PJ-008 | Term Sheet Agreed | 2026-02-21 | 2026-03-01 | 2026-03-01 | Complete
MS-0046 | PJ-008 | Legal & Compliance Review | 2026-04-14 | 2026-04-22 |  | Overdue
MS-0047 | PJ-008 | Signature | 2026-06-05 | 2026-06-16 |  | Overdue
MS-0048 | PJ-008 | Ratification Complete | 2026-07-27 | 2026-07-21 | 2026-07-21 | Complete
MS-0049 | PJ-008 | First Delivery Received | 2026-09-17 | 2026-09-11 |  | Planned
MS-0050 | PJ-009 | Mandate Approved | 2026-01-02 | 2026-01-18 | 2026-01-18 | Complete
MS-0051 | PJ-009 | Counterpart Engagement Opened | 2026-02-16 | 2026-03-05 | 2026-03-05 | Complete
MS-0052 | PJ-009 | Term Sheet Agreed | 2026-04-01 | 2026-04-17 |  | Overdue
MS-0053 | PJ-009 | Legal & Compliance Review | 2026-05-16 | 2026-05-17 |  | Overdue
MS-0054 | PJ-009 | Cabinet / Board Approval | 2026-06-30 | 2026-07-05 | 2026-07-05 | Complete
MS-0055 | PJ-009 | Signature | 2026-08-13 | 2026-08-10 | 2026-08-10 | Complete
MS-0056 | PJ-009 | First Delivery Received | 2026-09-27 | 2026-10-01 |  | Planned
MS-0057 | PJ-010 | Mandate Approved | 2026-08-14 | 2026-08-28 |  | Planned
MS-0058 | PJ-010 | Legal & Compliance Review | 2026-11-15 | 2026-12-16 |  | Planned
MS-0059 | PJ-010 | Signature | 2027-02-16 | 2027-03-09 |  | Planned
MS-0060 | PJ-010 | First Delivery Received | 2027-05-20 | 2027-06-30 |  | Planned
MS-0061 | PJ-011 | Mandate Approved | 2026-06-10 | 2026-06-08 | 2026-06-08 | Complete
MS-0062 | PJ-011 | Counterpart Engagement Opened | 2026-07-08 | 2026-07-02 | 2026-07-02 | Complete
MS-0063 | PJ-011 | Term Sheet Agreed | 2026-08-04 | 2026-08-16 | 2026-08-16 | Complete
MS-0064 | PJ-011 | Cabinet / Board Approval | 2026-09-01 | 2026-09-17 |  | Planned
MS-0065 | PJ-011 | Signature | 2026-09-29 | 2026-10-06 |  | Planned
MS-0066 | PJ-011 | Ratification Complete | 2026-10-26 | 2026-11-12 |  | Planned
MS-0067 | PJ-011 | First Delivery Received | 2026-11-23 | 2026-12-06 |  | Planned
MS-0068 | PJ-012 | Mandate Approved | 2026-03-30 | 2026-03-26 | 2026-03-26 | Complete
MS-0069 | PJ-012 | Counterpart Engagement Opened | 2026-05-10 | 2026-05-26 | 2026-05-26 | Complete
MS-0070 | PJ-012 | Term Sheet Agreed | 2026-06-20 | 2026-06-23 | 2026-06-23 | Complete
MS-0071 | PJ-012 | Legal & Compliance Review | 2026-07-31 | 2026-08-11 | 2026-08-11 | Complete
MS-0072 | PJ-012 | Signature | 2026-09-10 | 2026-09-04 |  | Planned
MS-0073 | PJ-012 | Ratification Complete | 2026-10-21 | 2026-10-24 |  | Planned
MS-0074 | PJ-012 | First Delivery Received | 2026-12-01 | 2026-12-24 |  | Planned
MS-0075 | PJ-013 | Land & Permits Secured | 2026-03-19 | 2026-06-07 | 2026-06-07 | Complete
MS-0076 | PJ-013 | Grid Connection Agreement | 2026-07-23 | 2026-11-26 |  | Planned
MS-0077 | PJ-013 | Design Authority Approval | 2026-11-26 | 2027-02-14 |  | Planned
MS-0078 | PJ-013 | Construction Start | 2027-04-01 | 2027-07-05 |  | Planned
MS-0079 | PJ-013 | Equipment Installation Complete | 2027-08-05 | 2027-12-06 |  | Planned
MS-0080 | PJ-013 | Commissioning & Test | 2027-12-09 | 2028-02-29 |  | Planned
MS-0081 | PJ-014 | Site Selection Approved | 2024-02-22 | 2024-03-08 | 2024-03-08 | Complete
MS-0082 | PJ-014 | Land & Permits Secured | 2024-07-24 | 2024-09-08 | 2024-09-08 | Complete
MS-0083 | PJ-014 | Grid Connection Agreement | 2024-12-24 | 2025-02-12 | 2025-02-12 | Complete
MS-0084 | PJ-014 | Power Energisation | 2025-05-26 | 2025-07-09 | 2025-07-09 | Complete
MS-0085 | PJ-014 | Equipment Installation Complete | 2025-10-26 | 2026-02-06 | 2026-02-06 | Complete
MS-0086 | PJ-014 | Commissioning & Test | 2026-03-28 | 2026-05-17 | 2026-05-17 | Complete
MS-0087 | PJ-014 | Operational Handover | 2026-08-28 | 2026-11-27 |  | Planned
MS-0088 | PJ-015 | Grid Connection Agreement | 2026-07-23 | 2026-08-09 |  | Overdue
MS-0089 | PJ-015 | Design Authority Approval | 2027-01-30 | 2027-02-14 |  | Planned
MS-0090 | PJ-015 | Construction Start | 2027-08-10 | 2027-08-22 |  | Planned
MS-0091 | PJ-015 | Equipment Installation Complete | 2028-02-17 | 2028-02-14 |  | Planned
MS-0092 | PJ-015 | Commissioning & Test | 2028-08-26 | 2028-09-10 |  | Planned
MS-0093 | PJ-016 | Site Selection Approved | 2024-01-10 | 2024-01-23 | 2024-01-23 | Complete
MS-0094 | PJ-016 | Land & Permits Secured | 2024-06-28 | 2024-06-30 | 2024-06-30 | Complete
MS-0095 | PJ-016 | Grid Connection Agreement | 2024-12-15 | 2024-12-15 | 2024-12-15 | Complete
MS-0096 | PJ-016 | Construction Start | 2025-06-03 | 2025-06-14 | 2025-06-14 | Complete
MS-0097 | PJ-016 | Power Energisation | 2025-11-20 | 2025-11-23 | 2025-11-23 | Complete
MS-0098 | PJ-016 | Operational Handover | 2026-05-09 | 2026-05-10 | 2026-05-10 | Complete
MS-0099 | PJ-017 | Site Selection Approved | 2024-08-01 | 2024-08-02 | 2024-08-02 | Complete
MS-0100 | PJ-017 | Grid Connection Agreement | 2024-12-09 | 2024-12-11 | 2024-12-11 | Complete
MS-0101 | PJ-017 | Design Authority Approval | 2025-04-17 | 2025-04-19 | 2025-04-19 | Complete
MS-0102 | PJ-017 | Power Energisation | 2025-08-25 | 2025-08-21 | 2025-08-21 | Complete
MS-0103 | PJ-017 | Equipment Installation Complete | 2026-01-02 | 2026-01-12 | 2026-01-12 | Complete
MS-0104 | PJ-017 | Commissioning & Test | 2026-05-11 | 2026-05-19 | 2026-05-19 | Complete
MS-0105 | PJ-017 | Operational Handover | 2026-09-18 | 2026-09-16 |  | Planned
MS-0106 | PJ-018 | Site Selection Approved | 2026-06-22 | 2026-07-02 | 2026-07-02 | Complete
MS-0107 | PJ-018 | Land & Permits Secured | 2026-11-01 | 2026-11-12 |  | Planned
MS-0108 | PJ-018 | Grid Connection Agreement | 2027-03-14 | 2027-03-25 |  | Planned
MS-0109 | PJ-018 | Power Energisation | 2027-07-24 | 2027-07-24 |  | Planned
MS-0110 | PJ-018 | Equipment Installation Complete | 2027-12-03 | 2027-11-28 |  | Planned
MS-0111 | PJ-019 | Architecture Baselined | 2024-12-24 | 2024-12-25 | 2024-12-25 | Complete
MS-0112 | PJ-019 | Data Access Agreed | 2025-03-15 | 2025-03-16 | 2025-03-16 | Complete
MS-0113 | PJ-019 | Build Complete | 2025-06-04 | 2025-06-06 |  | Overdue
MS-0114 | PJ-019 | Security Accreditation | 2025-08-24 | 2025-08-31 | 2025-08-31 | Complete
MS-0115 | PJ-019 | Evaluation & Red-Team Passed | 2025-11-12 | 2025-11-22 | 2025-11-22 | Complete
MS-0116 | PJ-019 | Production Go-Live | 2026-02-01 | 2026-02-08 |  | Overdue
MS-0117 | PJ-019 | Benefits Review | 2026-04-23 | 2026-04-26 | 2026-04-26 | Complete
MS-0118 | PJ-020 | Data Access Agreed | 2026-12-05 | 2026-12-09 |  | Planned
MS-0119 | PJ-020 | Environment Provisioned | 2027-06-02 | 2027-05-30 |  | Planned
MS-0120 | PJ-020 | Production Go-Live | 2027-11-27 | 2027-11-23 |  | Planned
MS-0121 | PJ-020 | Benefits Review | 2028-05-24 | 2028-05-28 |  | Planned
MS-0122 | PJ-021 | Business Case Approved | 2025-09-20 | 2025-10-05 | 2025-10-05 | Complete
MS-0123 | PJ-021 | Model Development Complete | 2025-12-01 | 2025-12-13 | 2025-12-13 | Complete
MS-0124 | PJ-021 | Pilot Live | 2026-02-11 | 2026-02-27 | 2026-02-27 | Complete
MS-0125 | PJ-021 | Change & Training Complete | 2026-04-24 | 2026-04-30 |  | Overdue
MS-0126 | PJ-022 | Business Case Approved | 2026-07-09 | 2026-07-19 | 2026-07-19 | Complete
MS-0127 | PJ-022 | Requirements Baselined | 2026-08-12 | 2026-08-10 |  | Overdue
MS-0128 | PJ-022 | Model Development Complete | 2026-09-15 | 2026-09-23 |  | Planned
MS-0129 | PJ-022 | Pilot Live | 2026-10-19 | 2026-10-14 |  | Planned
MS-0130 | PJ-022 | Change & Training Complete | 2026-11-21 | 2026-11-24 |  | Planned
MS-0131 | PJ-022 | Scaled Rollout | 2026-12-25 | 2027-01-06 |  | Planned
MS-0132 | PJ-022 | Benefits Review | 2027-01-28 | 2027-01-30 |  | Planned
MS-0133 | PJ-023 | Architecture Baselined | 2025-08-12 | 2025-08-21 |  | Overdue
MS-0134 | PJ-023 | Data Access Agreed | 2025-11-07 | 2025-11-06 | 2025-11-06 | Complete
MS-0135 | PJ-023 | Build Complete | 2026-02-02 | 2026-02-11 | 2026-02-11 | Complete
MS-0136 | PJ-023 | Evaluation & Red-Team Passed | 2026-04-30 | 2026-05-13 | 2026-05-13 | Complete
MS-0137 | PJ-023 | Benefits Review | 2026-07-26 | 2026-08-11 | 2026-08-11 | Complete
MS-0138 | PJ-024 | Mandate Approved | 2026-03-10 | 2026-03-11 | 2026-03-11 | Complete
MS-0139 | PJ-024 | Counterpart Engagement Opened | 2026-06-05 | 2026-06-20 | 2026-06-20 | Complete
MS-0140 | PJ-024 | Term Sheet Agreed | 2026-08-31 | 2026-09-23 |  | Planned
MS-0141 | PJ-024 | Signature | 2026-11-26 | 2026-12-23 |  | Planned
MS-0142 | PJ-024 | Ratification Complete | 2027-02-21 | 2027-02-16 |  | Planned
MS-0143 | PJ-024 | First Delivery Received | 2027-05-19 | 2027-06-08 |  | Planned
MS-0144 | PJ-025 | Counterpart Engagement Opened | 2026-01-10 | 2026-01-19 | 2026-01-19 | Complete
MS-0145 | PJ-025 | Term Sheet Agreed | 2026-04-11 | 2026-05-01 |  | Overdue
MS-0146 | PJ-025 | Cabinet / Board Approval | 2026-07-11 | 2026-07-28 | 2026-07-28 | Complete
MS-0147 | PJ-025 | First Delivery Received | 2026-10-10 | 2026-10-06 |  | Planned
MS-0148 | PJ-026 | Counterpart Engagement Opened | 2025-11-07 | 2025-11-02 | 2025-11-02 | Complete
MS-0149 | PJ-026 | Term Sheet Agreed | 2026-03-18 | 2026-04-04 | 2026-04-04 | Complete
MS-0150 | PJ-026 | Cabinet / Board Approval | 2026-07-27 | 2026-08-01 | 2026-08-01 | Complete
MS-0151 | PJ-026 | First Delivery Received | 2026-12-05 | 2026-12-04 |  | Planned
MS-0152 | PJ-027 | Counterpart Engagement Opened | 2026-08-31 | 2026-09-14 |  | Planned
MS-0153 | PJ-027 | Legal & Compliance Review | 2026-11-14 | 2026-11-27 |  | Planned
MS-0154 | PJ-027 | Cabinet / Board Approval | 2027-01-27 | 2027-02-12 |  | Planned
MS-0155 | PJ-027 | Signature | 2027-04-12 | 2027-04-27 |  | Planned
MS-0156 | PJ-028 | Site Selection Approved | 2026-06-14 | 2026-06-30 | 2026-06-30 | Complete
MS-0157 | PJ-028 | Design Authority Approval | 2026-08-27 | 2026-09-06 |  | Planned
MS-0158 | PJ-028 | Construction Start | 2026-11-09 | 2026-11-16 |  | Planned
MS-0159 | PJ-028 | Equipment Installation Complete | 2027-01-23 | 2027-02-08 |  | Planned
MS-0160 | PJ-028 | Commissioning & Test | 2027-04-07 | 2027-04-18 |  | Planned
MS-0161 | PJ-028 | Operational Handover | 2027-06-20 | 2027-06-21 |  | Planned
MS-0162 | PJ-029 | Mandate Approved | 2026-06-03 | 2026-06-15 | 2026-06-15 | Complete
MS-0163 | PJ-029 | Counterpart Engagement Opened | 2026-07-02 | 2026-07-19 | 2026-07-19 | Complete
MS-0164 | PJ-029 | Term Sheet Agreed | 2026-07-31 | 2026-08-18 |  | Planned
MS-0165 | PJ-029 | Cabinet / Board Approval | 2026-08-29 | 2026-09-07 |  | Planned
MS-0166 | PJ-029 | Signature | 2026-09-27 | 2026-10-05 |  | Planned
MS-0167 | PJ-029 | Ratification Complete | 2026-10-26 | 2026-11-01 |  | Planned
MS-0168 | PJ-030 | Design Authority Approval | 2025-09-15 | 2025-09-23 | 2025-09-23 | Complete
MS-0169 | PJ-030 | Construction Start | 2026-01-05 | 2026-01-09 | 2026-01-09 | Complete
MS-0170 | PJ-030 | Equipment Installation Complete | 2026-04-27 | 2026-04-23 | 2026-04-23 | Complete
MS-0171 | PJ-030 | Commissioning & Test | 2026-08-17 | 2026-08-25 |  | Planned
MS-0172 | PJ-031 | Mandate Approved | 2026-07-19 | 2026-07-31 | 2026-07-31 | Complete
MS-0173 | PJ-031 | Counterpart Engagement Opened | 2026-08-12 | 2026-08-10 | 2026-08-10 | Complete
MS-0174 | PJ-031 | Term Sheet Agreed | 2026-09-05 | 2026-09-07 |  | Planned
MS-0175 | PJ-031 | Cabinet / Board Approval | 2026-09-30 | 2026-10-02 |  | Planned
MS-0176 | PJ-031 | Signature | 2026-10-24 | 2026-10-31 |  | Planned
MS-0177 | PJ-031 | Ratification Complete | 2026-11-17 | 2026-11-18 |  | Planned
MS-0178 | PJ-031 | First Delivery Received | 2026-12-11 | 2026-12-05 |  | Planned
MS-0179 | PJ-032 | Business Case Approved | 2026-08-21 | 2026-08-15 | 2026-08-15 | Complete
MS-0180 | PJ-032 | Requirements Baselined | 2026-11-16 | 2026-11-25 |  | Planned
MS-0181 | PJ-032 | Change & Training Complete | 2027-02-10 | 2027-02-26 |  | Planned
MS-0182 | PJ-032 | Scaled Rollout | 2027-05-08 | 2027-05-14 |  | Planned
MS-0183 | PJ-032 | Benefits Review | 2027-08-02 | 2027-08-08 |  | Planned
MS-0184 | PJ-033 | Mandate Approved | 2026-08-12 | 2026-08-12 |  | Overdue
MS-0185 | PJ-033 | Counterpart Engagement Opened | 2026-09-19 | 2026-09-30 |  | Planned
MS-0186 | PJ-033 | Term Sheet Agreed | 2026-10-27 | 2026-11-05 |  | Planned
MS-0187 | PJ-033 | Cabinet / Board Approval | 2026-12-04 | 2026-12-09 |  | Planned
MS-0188 | PJ-033 | Ratification Complete | 2027-01-11 | 2027-01-10 |  | Planned
MS-0189 | PJ-034 | Architecture Baselined | 2025-12-09 | 2025-12-08 | 2025-12-08 | Complete
MS-0190 | PJ-034 | Data Access Agreed | 2026-02-07 | 2026-03-01 |  | Overdue
MS-0191 | PJ-034 | Security Accreditation | 2026-04-07 | 2026-04-29 | 2026-04-29 | Complete
MS-0192 | PJ-034 | Evaluation & Red-Team Passed | 2026-06-06 | 2026-06-07 | 2026-06-07 | Complete
MS-0193 | PJ-034 | Benefits Review | 2026-08-04 | 2026-08-09 | 2026-08-09 | Complete
MS-0194 | PJ-035 | Data Access Agreed | 2024-09-14 | 2024-09-14 | 2024-09-14 | Complete
MS-0195 | PJ-035 | Security Accreditation | 2025-03-10 | 2025-03-19 | 2025-03-19 | Complete
MS-0196 | PJ-035 | Evaluation & Red-Team Passed | 2025-09-03 | 2025-09-18 | 2025-09-18 | Complete
MS-0197 | PJ-035 | Benefits Review | 2026-02-27 | 2026-03-18 | 2026-03-18 | Complete
MS-0198 | PJ-036 | Data Access Agreed | 2025-11-14 | 2025-11-20 | 2025-11-20 | Complete
MS-0199 | PJ-036 | Environment Provisioned | 2026-01-22 | 2026-01-17 | 2026-01-17 | Complete
MS-0200 | PJ-036 | Build Complete | 2026-04-01 | 2026-05-02 | 2026-05-02 | Complete
MS-0201 | PJ-036 | Security Accreditation | 2026-06-09 | 2026-07-11 | 2026-07-11 | Complete
MS-0202 | PJ-036 | Evaluation & Red-Team Passed | 2026-08-17 | 2026-08-24 |  | Planned
MS-0203 | PJ-036 | Production Go-Live | 2026-10-25 | 2026-11-23 |  | Planned
MS-0204 | PJ-037 | Architecture Baselined | 2026-02-15 | 2026-02-25 | 2026-02-25 | Complete
MS-0205 | PJ-037 | Environment Provisioned | 2026-04-28 | 2026-05-29 |  | Overdue
MS-0206 | PJ-037 | Build Complete | 2026-07-09 | 2026-08-07 | 2026-08-07 | Complete
MS-0207 | PJ-037 | Security Accreditation | 2026-09-19 | 2026-09-29 |  | Planned
MS-0208 | PJ-037 | Evaluation & Red-Team Passed | 2026-11-30 | 2026-11-25 |  | Planned
MS-0209 | PJ-037 | Production Go-Live | 2027-02-10 | 2027-02-23 |  | Planned
MS-0210 | PJ-038 | Architecture Baselined | 2026-09-25 | 2026-12-02 |  | Planned
MS-0211 | PJ-038 | Data Access Agreed | 2027-01-22 | 2027-03-26 |  | Planned
MS-0212 | PJ-038 | Environment Provisioned | 2027-05-21 | 2027-07-31 |  | Planned
MS-0213 | PJ-038 | Build Complete | 2027-09-16 | 2027-09-21 |  | Planned
MS-0214 | PJ-038 | Security Accreditation | 2028-01-13 | 2028-02-23 |  | Planned
MS-0215 | PJ-038 | Evaluation & Red-Team Passed | 2028-05-11 | 2028-05-18 |  | Planned
MS-0216 | PJ-039 | Business Case Approved | 2026-06-09 | 2026-06-03 | 2026-06-03 | Complete
MS-0217 | PJ-039 | Requirements Baselined | 2026-07-28 | 2026-08-12 | 2026-08-12 | Complete
MS-0218 | PJ-039 | Pilot Live | 2026-09-15 | 2026-09-12 |  | Planned
MS-0219 | PJ-039 | Benefits Review | 2026-11-03 | 2026-10-29 |  | Planned
MS-0220 | PJ-040 | Business Case Approved | 2026-09-01 | 2026-10-08 |  | Planned
MS-0221 | PJ-040 | Requirements Baselined | 2026-10-28 | 2026-11-21 |  | Planned
MS-0222 | PJ-040 | Data Sharing Agreement | 2026-12-24 | 2027-01-07 |  | Planned
MS-0223 | PJ-040 | Model Development Complete | 2027-02-18 | 2027-03-09 |  | Planned
MS-0224 | PJ-040 | Scaled Rollout | 2027-04-16 | 2027-05-08 |  | Planned
MS-0225 | PJ-040 | Benefits Review | 2027-06-12 | 2027-06-26 |  | Planned
MS-0226 | PJ-041 | Requirements Baselined | 2026-01-12 | 2026-01-08 |  | Overdue
MS-0227 | PJ-041 | Data Sharing Agreement | 2026-03-06 | 2026-02-28 | 2026-02-28 | Complete
MS-0228 | PJ-041 | Model Development Complete | 2026-04-28 | 2026-04-28 | 2026-04-28 | Complete
MS-0229 | PJ-041 | Pilot Live | 2026-06-20 | 2026-06-25 | 2026-06-25 | Complete
MS-0230 | PJ-041 | Change & Training Complete | 2026-08-12 | 2026-08-12 | 2026-08-12 | Complete
MS-0231 | PJ-041 | Scaled Rollout | 2026-10-04 | 2026-10-09 |  | Planned
MS-0232 | PJ-041 | Benefits Review | 2026-11-26 | 2026-12-13 |  | Planned
MS-0233 | PJ-042 | Business Case Approved | 2025-12-28 | 2026-01-07 | 2026-01-07 | Complete
MS-0234 | PJ-042 | Requirements Baselined | 2026-01-27 | 2026-02-26 | 2026-02-26 | Complete
MS-0235 | PJ-042 | Data Sharing Agreement | 2026-02-26 | 2026-03-09 | 2026-03-09 | Complete
MS-0236 | PJ-042 | Model Development Complete | 2026-03-28 | 2026-05-01 | 2026-05-01 | Complete
MS-0237 | PJ-042 | Change & Training Complete | 2026-04-26 | 2026-05-13 |  | Overdue
MS-0238 | PJ-042 | Scaled Rollout | 2026-05-26 | 2026-06-15 |  | Overdue
MS-0239 | PJ-042 | Benefits Review | 2026-06-25 | 2026-07-11 | 2026-07-11 | Complete
MS-0240 | PJ-043 | Environment Provisioned | 2025-08-30 | 2025-09-15 | 2025-09-15 | Complete
MS-0241 | PJ-043 | Build Complete | 2025-10-29 | 2025-11-08 | 2025-11-08 | Complete
MS-0242 | PJ-043 | Security Accreditation | 2025-12-28 | 2026-01-05 | 2026-01-05 | Complete
MS-0243 | PJ-043 | Production Go-Live | 2026-02-25 | 2026-02-20 | 2026-02-20 | Complete
MS-0244 | PJ-043 | Benefits Review | 2026-04-26 | 2026-05-09 | 2026-05-09 | Complete
MS-0245 | PJ-044 | Business Case Approved | 2025-08-30 | 2025-08-24 |  | Overdue
MS-0246 | PJ-044 | Requirements Baselined | 2025-11-04 | 2025-11-12 | 2025-11-12 | Complete
MS-0247 | PJ-044 | Data Sharing Agreement | 2026-01-08 | 2026-01-25 | 2026-01-25 | Complete
MS-0248 | PJ-044 | Pilot Live | 2026-03-15 | 2026-03-14 |  | Overdue
MS-0249 | PJ-044 | Change & Training Complete | 2026-05-20 | 2026-05-26 | 2026-05-26 | Complete
MS-0250 | PJ-044 | Scaled Rollout | 2026-07-24 | 2026-08-03 | 2026-08-03 | Complete
MS-0251 | PJ-044 | Benefits Review | 2026-09-28 | 2026-10-21 |  | Planned
MS-0252 | PJ-045 | Data Sharing Agreement | 2026-01-11 | 2026-01-25 | 2026-01-25 | Complete
MS-0253 | PJ-045 | Model Development Complete | 2026-02-18 | 2026-02-18 |  | Overdue
MS-0254 | PJ-045 | Pilot Live | 2026-03-28 | 2026-03-25 | 2026-03-25 | Complete
MS-0255 | PJ-045 | Change & Training Complete | 2026-05-04 | 2026-05-06 |  | Overdue
MS-0256 | PJ-045 | Scaled Rollout | 2026-06-11 | 2026-06-13 | 2026-06-13 | Complete
MS-0257 | PJ-045 | Benefits Review | 2026-07-19 | 2026-07-21 | 2026-07-21 | Complete
MS-0258 | PJ-046 | Architecture Baselined | 2026-01-05 | 2026-01-10 | 2026-01-10 | Complete
MS-0259 | PJ-046 | Environment Provisioned | 2026-03-21 | 2026-03-25 |  | Overdue
MS-0260 | PJ-046 | Build Complete | 2026-06-04 | 2026-06-19 | 2026-06-19 | Complete
MS-0261 | PJ-046 | Evaluation & Red-Team Passed | 2026-08-18 | 2026-09-04 |  | Planned
MS-0262 | PJ-046 | Production Go-Live | 2026-11-01 | 2026-11-14 |  | Planned
MS-0263 | PJ-047 | Business Case Approved | 2026-08-11 | 2026-08-28 |  | Planned
MS-0264 | PJ-047 | Requirements Baselined | 2026-09-29 | 2026-10-08 |  | Planned
MS-0265 | PJ-047 | Scaled Rollout | 2026-11-17 | 2026-11-25 |  | Planned
MS-0266 | PJ-047 | Benefits Review | 2027-01-05 | 2027-01-13 |  | Planned
MS-0267 | PJ-048 | Business Case Approved | 2026-06-07 | 2026-06-20 | 2026-06-20 | Complete
MS-0268 | PJ-048 | Data Sharing Agreement | 2026-07-18 | 2026-08-05 |  | Overdue
MS-0269 | PJ-048 | Model Development Complete | 2026-08-29 | 2026-09-21 |  | Planned
MS-0270 | PJ-048 | Pilot Live | 2026-10-09 | 2026-10-29 |  | Planned
MS-0271 | PJ-048 | Change & Training Complete | 2026-11-20 | 2026-12-07 |  | Planned
MS-0272 | PJ-048 | Scaled Rollout | 2026-12-31 | 2026-12-25 |  | Planned
MS-0273 | PJ-049 | Requirements Baselined | 2026-06-08 | 2026-06-17 | 2026-06-17 | Complete
MS-0274 | PJ-049 | Model Development Complete | 2026-07-12 | 2026-07-29 | 2026-07-29 | Complete
MS-0275 | PJ-049 | Scaled Rollout | 2026-08-15 | 2026-08-09 | 2026-08-09 | Complete
MS-0276 | PJ-049 | Benefits Review | 2026-09-18 | 2026-10-10 |  | Planned
MS-0277 | PJ-050 | Model Development Complete | 2025-09-06 | 2025-09-02 | 2025-09-02 | Complete
MS-0278 | PJ-050 | Change & Training Complete | 2025-12-18 | 2025-12-17 | 2025-12-17 | Complete
MS-0279 | PJ-050 | Scaled Rollout | 2026-03-31 | 2026-04-03 | 2026-04-03 | Complete
MS-0280 | PJ-050 | Benefits Review | 2026-07-12 | 2026-07-21 | 2026-07-21 | Complete
MS-0281 | PJ-051 | Business Case Approved | 2026-03-10 | 2026-03-14 |  | Overdue
MS-0282 | PJ-051 | Requirements Baselined | 2026-05-15 | 2026-05-18 | 2026-05-18 | Complete
MS-0283 | PJ-051 | Data Sharing Agreement | 2026-07-20 | 2026-07-15 | 2026-07-15 | Complete
MS-0284 | PJ-051 | Model Development Complete | 2026-09-24 | 2026-09-27 |  | Planned
MS-0285 | PJ-051 | Change & Training Complete | 2026-11-29 | 2026-11-30 |  | Planned
MS-0286 | PJ-051 | Scaled Rollout | 2027-02-03 | 2027-02-04 |  | Planned
MS-0287 | PJ-052 | Data Sharing Agreement | 2026-08-24 | 2026-09-03 |  | Planned
MS-0288 | PJ-052 | Model Development Complete | 2026-11-14 | 2026-11-08 |  | Planned
MS-0289 | PJ-052 | Pilot Live | 2027-02-04 | 2027-02-19 |  | Planned
MS-0290 | PJ-052 | Change & Training Complete | 2027-04-27 | 2027-05-13 |  | Planned
MS-0291 | PJ-052 | Benefits Review | 2027-07-18 | 2027-07-22 |  | Planned
MS-0292 | PJ-053 | Business Case Approved | 2025-12-12 | 2025-12-31 | 2025-12-31 | Complete
MS-0293 | PJ-053 | Data Sharing Agreement | 2026-03-22 | 2026-03-25 | 2026-03-25 | Complete
MS-0294 | PJ-053 | Model Development Complete | 2026-06-30 | 2026-07-26 | 2026-07-26 | Complete
MS-0295 | PJ-053 | Benefits Review | 2026-10-08 | 2026-10-09 |  | Planned
MS-0296 | PJ-054 | Business Case Approved | 2025-10-04 | 2025-10-11 | 2025-10-11 | Complete
MS-0297 | PJ-054 | Requirements Baselined | 2026-01-11 | 2026-01-24 | 2026-01-24 | Complete
MS-0298 | PJ-054 | Data Sharing Agreement | 2026-04-20 | 2026-05-02 | 2026-05-02 | Complete
MS-0299 | PJ-054 | Change & Training Complete | 2026-07-28 | 2026-07-26 | 2026-07-26 | Complete
MS-0300 | PJ-055 | Business Case Approved | 2026-03-04 | 2026-03-16 | 2026-03-16 | Complete
MS-0301 | PJ-055 | Requirements Baselined | 2026-05-04 | 2026-05-21 |  | Overdue
MS-0302 | PJ-055 | Data Sharing Agreement | 2026-07-04 | 2026-07-19 | 2026-07-19 | Complete
MS-0303 | PJ-055 | Change & Training Complete | 2026-09-03 | 2026-09-02 |  | Planned
MS-0304 | PJ-055 | Scaled Rollout | 2026-11-03 | 2026-11-16 |  | Planned
MS-0305 | PJ-055 | Benefits Review | 2027-01-03 | 2027-01-13 |  | Planned
MS-0306 | PJ-056 | Architecture Baselined | 2026-03-01 | 2026-03-04 | 2026-03-04 | Complete
MS-0307 | PJ-056 | Data Access Agreed | 2026-05-28 | 2026-06-08 | 2026-06-08 | Complete
MS-0308 | PJ-056 | Environment Provisioned | 2026-08-24 | 2026-09-05 |  | Planned
MS-0309 | PJ-056 | Security Accreditation | 2026-11-20 | 2026-11-27 |  | Planned
MS-0310 | PJ-056 | Benefits Review | 2027-02-16 | 2027-02-27 |  | Planned
MS-0311 | PJ-057 | Business Case Approved | 2026-01-06 | 2026-01-22 | 2026-01-22 | Complete
MS-0312 | PJ-057 | Requirements Baselined | 2026-03-17 | 2026-03-15 |  | Overdue
MS-0313 | PJ-057 | Data Sharing Agreement | 2026-05-25 | 2026-05-20 | 2026-05-20 | Complete
MS-0314 | PJ-057 | Model Development Complete | 2026-08-03 | 2026-08-04 | 2026-08-04 | Complete
MS-0315 | PJ-057 | Pilot Live | 2026-10-12 | 2026-10-22 |  | Planned
MS-0316 | PJ-057 | Change & Training Complete | 2026-12-20 | 2027-01-01 |  | Planned
MS-0317 | PJ-057 | Scaled Rollout | 2027-02-28 | 2027-03-11 |  | Planned
MS-0318 | PJ-058 | Business Case Approved | 2026-05-19 | 2026-05-17 |  | Overdue
MS-0319 | PJ-058 | Requirements Baselined | 2026-07-21 | 2026-08-02 | 2026-08-02 | Complete
MS-0320 | PJ-058 | Data Sharing Agreement | 2026-09-22 | 2026-09-20 |  | Planned
MS-0321 | PJ-058 | Pilot Live | 2026-11-25 | 2027-01-01 |  | Planned
MS-0322 | PJ-058 | Scaled Rollout | 2027-01-27 | 2027-03-03 |  | Planned
MS-0323 | PJ-058 | Benefits Review | 2027-03-31 | 2027-05-02 |  | Planned
MS-0324 | PJ-059 | Business Case Approved | 2026-01-06 | 2026-01-10 |  | Overdue
MS-0325 | PJ-059 | Requirements Baselined | 2026-02-08 | 2026-02-17 | 2026-02-17 | Complete
MS-0326 | PJ-059 | Data Sharing Agreement | 2026-03-13 | 2026-03-26 | 2026-03-26 | Complete
MS-0327 | PJ-059 | Model Development Complete | 2026-04-15 | 2026-04-28 | 2026-04-28 | Complete
MS-0328 | PJ-059 | Pilot Live | 2026-05-17 | 2026-05-18 | 2026-05-18 | Complete
MS-0329 | PJ-059 | Change & Training Complete | 2026-06-19 | 2026-06-22 | 2026-06-22 | Complete
MS-0330 | PJ-059 | Scaled Rollout | 2026-07-22 | 2026-07-17 | 2026-07-17 | Complete
MS-0331 | PJ-060 | Business Case Approved | 2026-05-08 | 2026-05-17 |  | Overdue
MS-0332 | PJ-060 | Data Sharing Agreement | 2026-06-29 | 2026-06-30 | 2026-06-30 | Complete
MS-0333 | PJ-060 | Model Development Complete | 2026-08-20 | 2026-08-15 | 2026-08-15 | Complete
MS-0334 | PJ-060 | Pilot Live | 2026-10-11 | 2026-10-10 |  | Planned
MS-0335 | PJ-061 | Architecture Baselined | 2025-06-26 | 2025-07-11 | 2025-07-11 | Complete
MS-0336 | PJ-061 | Data Access Agreed | 2025-09-11 | 2025-09-08 | 2025-09-08 | Complete
MS-0337 | PJ-061 | Environment Provisioned | 2025-11-26 | 2025-12-09 | 2025-12-09 | Complete
MS-0338 | PJ-061 | Build Complete | 2026-02-11 | 2026-02-06 | 2026-02-06 | Complete
MS-0339 | PJ-061 | Security Accreditation | 2026-04-29 | 2026-05-13 | 2026-05-13 | Complete
MS-0340 | PJ-061 | Evaluation & Red-Team Passed | 2026-07-14 | 2026-07-18 | 2026-07-18 | Complete
MS-0341 | PJ-061 | Production Go-Live | 2026-09-29 | 2026-10-16 |  | Planned
MS-0342 | PJ-062 | Requirements Baselined | 2025-11-10 | 2025-11-06 | 2025-11-06 | Complete
MS-0343 | PJ-062 | Data Sharing Agreement | 2025-12-11 | 2025-12-20 | 2025-12-20 | Complete
MS-0344 | PJ-062 | Model Development Complete | 2026-01-11 | 2026-01-12 | 2026-01-12 | Complete
MS-0345 | PJ-062 | Pilot Live | 2026-02-11 | 2026-02-20 | 2026-02-20 | Complete
MS-0346 | PJ-062 | Change & Training Complete | 2026-03-14 | 2026-03-23 | 2026-03-23 | Complete
MS-0347 | PJ-062 | Scaled Rollout | 2026-04-14 | 2026-05-09 | 2026-05-09 | Complete
MS-0348 | PJ-062 | Benefits Review | 2026-05-15 | 2026-06-05 | 2026-06-05 | Complete
MS-0349 | PJ-063 | Business Case Approved | 2026-04-06 | 2026-04-15 | 2026-04-15 | Complete
MS-0350 | PJ-063 | Requirements Baselined | 2026-06-14 | 2026-06-10 | 2026-06-10 | Complete
MS-0351 | PJ-063 | Model Development Complete | 2026-08-23 | 2026-08-24 |  | Planned
MS-0352 | PJ-063 | Pilot Live | 2026-10-31 | 2026-11-11 |  | Planned
MS-0353 | PJ-063 | Change & Training Complete | 2027-01-09 | 2027-01-19 |  | Planned
MS-0354 | PJ-063 | Benefits Review | 2027-03-19 | 2027-03-23 |  | Planned
MS-0355 | PJ-064 | Architecture Baselined | 2026-06-14 | 2026-06-16 |  | Overdue
MS-0356 | PJ-064 | Data Access Agreed | 2026-10-02 | 2026-10-09 |  | Planned
MS-0357 | PJ-064 | Build Complete | 2027-01-19 | 2027-04-09 |  | Planned
MS-0358 | PJ-064 | Security Accreditation | 2027-05-09 | 2027-06-26 |  | Planned
MS-0359 | PJ-064 | Production Go-Live | 2027-08-26 | 2027-08-29 |  | Planned
MS-0360 | PJ-064 | Benefits Review | 2027-12-14 | 2028-02-16 |  | Planned
MS-0361 | PJ-065 | Site Selection Approved | 2026-03-11 | 2026-03-18 | 2026-03-18 | Complete
MS-0362 | PJ-065 | Grid Connection Agreement | 2026-09-01 | 2026-09-01 |  | Planned
MS-0363 | PJ-065 | Design Authority Approval | 2027-02-21 | 2027-03-08 |  | Planned
MS-0364 | PJ-065 | Construction Start | 2027-08-14 | 2027-08-30 |  | Planned
MS-0365 | PJ-065 | Power Energisation | 2028-02-04 | 2028-02-03 |  | Planned
MS-0366 | PJ-065 | Equipment Installation Complete | 2028-07-26 | 2028-08-08 |  | Planned
MS-0367 | PJ-065 | Operational Handover | 2029-01-16 | 2029-01-31 |  | Planned
MS-0368 | PJ-066 | Architecture Baselined | 2025-09-21 | 2025-09-22 | 2025-09-22 | Complete
MS-0369 | PJ-066 | Data Access Agreed | 2026-01-04 | 2026-01-14 | 2026-01-14 | Complete
MS-0370 | PJ-066 | Environment Provisioned | 2026-04-19 | 2026-04-23 | 2026-04-23 | Complete
MS-0371 | PJ-066 | Build Complete | 2026-08-03 | 2026-08-11 | 2026-08-11 | Complete
MS-0372 | PJ-066 | Security Accreditation | 2026-11-16 | 2026-11-15 |  | Planned
MS-0373 | PJ-066 | Evaluation & Red-Team Passed | 2027-03-01 | 2027-03-01 |  | Planned
MS-0374 | PJ-066 | Benefits Review | 2027-06-14 | 2027-06-20 |  | Planned
MS-0375 | PJ-067 | Business Case Approved | 2026-03-22 | 2026-04-21 | 2026-04-21 | Complete
MS-0376 | PJ-067 | Requirements Baselined | 2026-05-20 | 2026-06-25 | 2026-06-25 | Complete
MS-0377 | PJ-067 | Data Sharing Agreement | 2026-07-18 | 2026-08-14 | 2026-08-14 | Complete
MS-0378 | PJ-067 | Model Development Complete | 2026-09-15 | 2026-10-03 |  | Planned
MS-0379 | PJ-067 | Pilot Live | 2026-11-13 | 2026-11-29 |  | Planned
MS-0380 | PJ-067 | Benefits Review | 2027-01-11 | 2027-02-05 |  | Planned
MS-0381 | PJ-068 | Land & Permits Secured | 2025-06-22 | 2025-07-29 |  | Overdue
MS-0382 | PJ-068 | Grid Connection Agreement | 2025-12-05 | 2026-02-17 | 2026-02-17 | Complete
MS-0383 | PJ-068 | Design Authority Approval | 2026-05-19 | 2026-05-27 | 2026-05-27 | Complete
MS-0384 | PJ-068 | Construction Start | 2026-11-01 | 2027-01-16 |  | Planned
MS-0385 | PJ-068 | Equipment Installation Complete | 2027-04-15 | 2027-07-02 |  | Planned
MS-0386 | PJ-068 | Commissioning & Test | 2027-09-28 | 2027-10-09 |  | Planned
MS-0387 | PJ-069 | Business Case Approved | 2026-02-20 | 2026-03-07 |  | Overdue
MS-0388 | PJ-069 | Requirements Baselined | 2026-04-21 | 2026-04-28 | 2026-04-28 | Complete
MS-0389 | PJ-069 | Data Sharing Agreement | 2026-06-19 | 2026-06-23 | 2026-06-23 | Complete
MS-0390 | PJ-069 | Model Development Complete | 2026-08-18 | 2026-08-16 |  | Planned
MS-0391 | PJ-069 | Pilot Live | 2026-10-17 | 2026-10-22 |  | Planned
MS-0392 | PJ-069 | Scaled Rollout | 2026-12-15 | 2026-12-29 |  | Planned
MS-0393 | PJ-069 | Benefits Review | 2027-02-13 | 2027-02-27 |  | Planned
MS-0394 | PJ-070 | Architecture Baselined | 2025-10-24 | 2025-11-04 | 2025-11-04 | Complete
MS-0395 | PJ-070 | Security Accreditation | 2026-01-06 | 2026-01-18 | 2026-01-18 | Complete
MS-0396 | PJ-070 | Evaluation & Red-Team Passed | 2026-03-22 | 2026-04-01 | 2026-04-01 | Complete
MS-0397 | PJ-070 | Production Go-Live | 2026-06-04 | 2026-06-09 | 2026-06-09 | Complete
MS-0398 | PJ-071 | Business Case Approved | 2025-10-14 | 2025-10-10 | 2025-10-10 | Complete
MS-0399 | PJ-071 | Requirements Baselined | 2025-12-18 | 2026-01-16 |  | Overdue
MS-0400 | PJ-071 | Data Sharing Agreement | 2026-02-20 | 2026-04-10 | 2026-04-10 | Complete
MS-0401 | PJ-071 | Model Development Complete | 2026-04-26 | 2026-06-08 | 2026-06-08 | Complete
MS-0402 | PJ-071 | Pilot Live | 2026-06-29 | 2026-07-07 | 2026-07-07 | Complete
MS-0403 | PJ-071 | Change & Training Complete | 2026-09-02 | 2026-10-18 |  | Planned
MS-0404 | PJ-071 | Benefits Review | 2026-11-05 | 2026-12-19 |  | Planned
MS-0405 | PJ-072 | Site Selection Approved | 2026-12-11 | 2026-12-27 |  | Planned
MS-0406 | PJ-072 | Design Authority Approval | 2027-08-31 | 2027-09-12 |  | Planned
MS-0407 | PJ-072 | Commissioning & Test | 2028-05-21 | 2028-05-18 |  | Planned
MS-0408 | PJ-072 | Operational Handover | 2029-02-08 | 2029-02-17 |  | Planned
MS-0409 | PJ-073 | Pilot Live | 2026-07-07 | 2026-07-24 | 2026-07-24 | Complete
MS-0410 | PJ-073 | Change & Training Complete | 2026-09-16 | 2026-09-24 |  | Planned
MS-0411 | PJ-073 | Scaled Rollout | 2026-11-26 | 2026-12-12 |  | Planned
MS-0412 | PJ-073 | Benefits Review | 2027-02-05 | 2027-02-07 |  | Planned
MS-0413 | PJ-074 | Architecture Baselined | 2026-10-15 | 2026-10-30 |  | Planned
MS-0414 | PJ-074 | Data Access Agreed | 2027-01-04 | 2027-01-11 |  | Planned
MS-0415 | PJ-074 | Environment Provisioned | 2027-03-27 | 2027-04-03 |  | Planned
MS-0416 | PJ-074 | Security Accreditation | 2027-06-16 | 2027-06-16 |  | Planned
MS-0417 | PJ-074 | Benefits Review | 2027-09-05 | 2027-09-08 |  | Planned
MS-0418 | PJ-075 | Requirements Baselined | 2026-04-28 | 2026-05-03 |  | Overdue
MS-0419 | PJ-075 | Data Sharing Agreement | 2026-06-27 | 2026-06-29 |  | Overdue
MS-0420 | PJ-075 | Model Development Complete | 2026-08-26 | 2026-08-24 |  | Planned
MS-0421 | PJ-075 | Change & Training Complete | 2026-10-25 | 2026-11-02 |  | Planned
MS-0422 | PJ-075 | Scaled Rollout | 2026-12-24 | 2027-01-01 |  | Planned
MS-0423 | PJ-075 | Benefits Review | 2027-02-22 | 2027-02-16 |  | Planned
MS-0424 | PJ-076 | Business Case Approved | 2026-07-19 | 2026-07-27 | 2026-07-27 | Complete
MS-0425 | PJ-076 | Requirements Baselined | 2026-09-13 | 2026-09-15 |  | Planned
MS-0426 | PJ-076 | Data Sharing Agreement | 2026-11-07 | 2026-11-04 |  | Planned
MS-0427 | PJ-076 | Pilot Live | 2027-01-02 | 2027-01-18 |  | Planned
MS-0428 | PJ-076 | Change & Training Complete | 2027-02-26 | 2027-02-20 |  | Planned
MS-0429 | PJ-076 | Scaled Rollout | 2027-04-23 | 2027-04-20 |  | Planned
MS-0430 | PJ-076 | Benefits Review | 2027-06-17 | 2027-06-28 |  | Planned
MS-0431 | PJ-077 | Site Selection Approved | 2026-06-13 | 2026-06-14 | 2026-06-14 | Complete
MS-0432 | PJ-077 | Land & Permits Secured | 2027-01-21 | 2027-01-25 |  | Planned
MS-0433 | PJ-077 | Grid Connection Agreement | 2027-08-31 | 2027-09-13 |  | Planned
MS-0434 | PJ-077 | Construction Start | 2028-04-09 | 2028-04-05 |  | Planned
MS-0435 | PJ-078 | Business Case Approved | 2026-03-02 | 2026-03-06 | 2026-03-06 | Complete
MS-0436 | PJ-078 | Requirements Baselined | 2026-04-15 | 2026-04-14 | 2026-04-14 | Complete
MS-0437 | PJ-078 | Model Development Complete | 2026-05-29 | 2026-06-01 | 2026-06-01 | Complete
MS-0438 | PJ-078 | Pilot Live | 2026-07-13 | 2026-07-27 | 2026-07-27 | Complete
MS-0439 | PJ-078 | Change & Training Complete | 2026-08-26 | 2026-09-07 |  | Planned
MS-0440 | PJ-078 | Scaled Rollout | 2026-10-09 | 2026-10-25 |  | Planned
MS-0441 | PJ-078 | Benefits Review | 2026-11-22 | 2026-12-03 |  | Planned
MS-0442 | PJ-079 | Business Case Approved | 2026-09-12 | 2026-10-02 |  | Planned
MS-0443 | PJ-079 | Model Development Complete | 2026-11-06 | 2026-11-05 |  | Planned
MS-0444 | PJ-079 | Pilot Live | 2027-01-01 | 2027-01-25 |  | Planned
MS-0445 | PJ-079 | Scaled Rollout | 2027-02-25 | 2027-03-22 |  | Planned
MS-0446 | PJ-080 | Business Case Approved | 2026-02-26 | 2026-02-21 | 2026-02-21 | Complete
MS-0447 | PJ-080 | Requirements Baselined | 2026-04-12 | 2026-04-21 | 2026-04-21 | Complete
MS-0448 | PJ-080 | Data Sharing Agreement | 2026-05-27 | 2026-05-28 | 2026-05-28 | Complete
MS-0449 | PJ-080 | Model Development Complete | 2026-07-12 | 2026-07-22 | 2026-07-22 | Complete
MS-0450 | PJ-080 | Pilot Live | 2026-08-26 | 2026-08-22 |  | Planned
MS-0451 | PJ-080 | Change & Training Complete | 2026-10-10 | 2026-10-07 |  | Planned
MS-0452 | PJ-080 | Scaled Rollout | 2026-11-24 | 2026-11-26 |  | Planned
MS-0453 | PJ-081 | Architecture Baselined | 2025-12-03 | 2025-12-05 | 2025-12-05 | Complete
MS-0454 | PJ-081 | Environment Provisioned | 2026-01-28 | 2026-02-06 | 2026-02-06 | Complete
MS-0455 | PJ-081 | Build Complete | 2026-03-25 | 2026-04-07 | 2026-04-07 | Complete
MS-0456 | PJ-081 | Security Accreditation | 2026-05-20 | 2026-05-31 | 2026-05-31 | Complete
MS-0457 | PJ-081 | Evaluation & Red-Team Passed | 2026-07-15 | 2026-07-18 | 2026-07-18 | Complete
MS-0458 | PJ-081 | Production Go-Live | 2026-09-09 | 2026-09-18 |  | Planned
MS-0459 | PJ-081 | Benefits Review | 2026-11-04 | 2026-11-06 |  | Planned
MS-0460 | PJ-082 | Data Sharing Agreement | 2026-06-16 | 2026-06-24 | 2026-06-24 | Complete
MS-0461 | PJ-082 | Model Development Complete | 2026-07-12 | 2026-07-23 | 2026-07-23 | Complete
MS-0462 | PJ-082 | Pilot Live | 2026-08-07 | 2026-08-06 | 2026-08-06 | Complete
MS-0463 | PJ-082 | Change & Training Complete | 2026-09-02 | 2026-09-03 |  | Planned
MS-0464 | PJ-082 | Scaled Rollout | 2026-09-28 | 2026-10-04 |  | Planned
MS-0465 | PJ-083 | Model Development Complete | 2025-10-22 | 2025-11-12 | 2025-11-12 | Complete
MS-0466 | PJ-083 | Pilot Live | 2026-02-05 | 2026-03-15 | 2026-03-15 | Complete
MS-0467 | PJ-083 | Change & Training Complete | 2026-05-21 | 2026-05-23 | 2026-05-23 | Complete
MS-0468 | PJ-083 | Benefits Review | 2026-09-04 | 2026-10-20 |  | Planned
MS-0469 | PJ-084 | Data Sharing Agreement | 2026-03-17 | 2026-04-10 | 2026-04-10 | Complete
MS-0470 | PJ-084 | Model Development Complete | 2026-06-18 | 2026-07-15 | 2026-07-15 | Complete
MS-0471 | PJ-084 | Change & Training Complete | 2026-09-19 | 2026-10-30 |  | Planned
MS-0472 | PJ-084 | Scaled Rollout | 2026-12-21 | 2026-12-30 |  | Planned
MS-0473 | PJ-084 | Benefits Review | 2027-03-24 | 2027-04-12 |  | Planned

## Risks
RiskID | ProjectID | RiskTitle | Category | Probability | Impact | Response | Owner | Status | DueDate | Exposure
RK-0001 | PJ-001 | Land handover contingent on unresolved zoning approval | Regulatory | 2 | 5 | Avoid | R. Nakamura | Open | 2026-09-05
RK-0002 | PJ-001 | Transformer and switchgear lead times exceed 18 months | Supply Chain | 2 | 3 | Transfer | R. Nakamura | Open | 2027-03-20
RK-0003 | PJ-001 | Cooling plant single-sourced with no qualified alternate | Supply Chain | 2 | 3 | Transfer | R. Nakamura | Open | 2026-07-02
RK-0004 | PJ-002 | Land handover contingent on unresolved zoning approval | Regulatory | 1 | 2 | Accept | R. Nakamura | Open | 2027-02-15
RK-0005 | PJ-002 | Construction labour availability in peak season | Resource | 5 | 2 | Transfer | R. Nakamura | Open | 2026-09-12
RK-0006 | PJ-002 | Water availability constraint at campus site | Environmental | 3 | 3 | Mitigate | R. Nakamura | Monitoring | 2027-02-17
RK-0007 | PJ-003 | Commissioning window collides with summer peak load | Schedule | 2 | 5 | Transfer | R. Nakamura | Open | 2027-05-06
RK-0008 | PJ-003 | Cooling plant single-sourced with no qualified alternate | Supply Chain | 1 | 5 | Accept | R. Nakamura | Open | 2026-11-23
RK-0009 | PJ-003 | Grid connection date slips beyond facility readiness | Energy & Grid | 3 | 5 | Transfer | R. Nakamura | Monitoring | 2027-01-07
RK-0010 | PJ-003 | Land handover contingent on unresolved zoning approval | Regulatory | 2 | 1 | Mitigate | R. Nakamura | Closed | 2026-11-28
RK-0011 | PJ-003 | Construction labour availability in peak season | Resource | 2 | 3 | Accept | R. Nakamura | Monitoring | 2026-06-05
RK-0012 | PJ-004 | Water availability constraint at campus site | Environmental | 2 | 3 | Mitigate | R. Nakamura | Open | 2026-08-04
RK-0013 | PJ-004 | Construction labour availability in peak season | Resource | 3 | 4 | Accept | R. Nakamura | Open | 2027-03-09
RK-0014 | PJ-005 | Escalation in structural steel and copper pricing | Cost | 3 | 4 | Transfer | R. Nakamura | Closed | 2027-03-25
RK-0015 | PJ-005 | Transformer and switchgear lead times exceed 18 months | Supply Chain | 4 | 1 | Avoid | R. Nakamura | Open | 2026-09-25
RK-0016 | PJ-005 | Grid connection date slips beyond facility readiness | Energy & Grid | 3 | 2 | Transfer | R. Nakamura | Open | 2027-03-25
RK-0017 | PJ-005 | Land handover contingent on unresolved zoning approval | Regulatory | 1 | 4 | Accept | R. Nakamura | Closed | 2026-06-05
RK-0018 | PJ-006 | Cybersecurity accreditation not complete before go-live | Cyber | 5 | 1 | Mitigate | R. Nakamura | Monitoring | 2026-10-25
RK-0019 | PJ-006 | Upstream data quality insufficient for target accuracy | Technical | 2 | 3 | Transfer | R. Nakamura | Monitoring | 2027-04-05
RK-0020 | PJ-006 | Training run may not converge within allocated compute budget | Technical | 5 | 3 | Avoid | R. Nakamura | Open | 2026-06-26
RK-0021 | PJ-006 | Model evaluation standards not yet defined by regulator | Regulatory | 1 | 3 | Avoid | R. Nakamura | Monitoring | 2027-05-04
RK-0022 | PJ-006 | Benchmark performance unverified at production scale | Technical | 1 | 3 | Avoid | R. Nakamura | Monitoring | 2026-09-15
RK-0023 | PJ-007 | Sanctions regime change affects delivery route | Geopolitical | 2 | 3 | Accept | L. Bergstrom | Closed | 2026-07-30
RK-0024 | PJ-007 | Counterpart legal review extends beyond target signature | Schedule | 4 | 1 | Accept | L. Bergstrom | Open | 2026-09-27
RK-0025 | PJ-007 | Currency exposure on multi-year hardware commitment | Cost | 1 | 4 | Accept | L. Bergstrom | Closed | 2026-12-25
RK-0026 | PJ-007 | Chip allocation reduced by vendor under global demand | Supply Chain | 3 | 1 | Avoid | L. Bergstrom | Open | 2027-02-21
RK-0027 | PJ-007 | Export licence approval slower than programme assumption | Geopolitical | 2 | 3 | Avoid | L. Bergstrom | Closed | 2026-09-07
RK-0028 | PJ-007 | Counterpart position may shift after national elections | Geopolitical | 3 | 4 | Avoid | L. Bergstrom | Monitoring | 2027-01-06
RK-0029 | PJ-008 | Offset and local-content obligations not yet costed | Cost | 2 | 2 | Avoid | L. Bergstrom | Open | 2026-10-18
RK-0030 | PJ-008 | Export licence approval slower than programme assumption | Geopolitical | 4 | 3 | Accept | L. Bergstrom | Monitoring | 2026-05-29
RK-0031 | PJ-008 | Counterpart legal review extends beyond target signature | Schedule | 3 | 4 | Transfer | L. Bergstrom | Open | 2026-10-09
RK-0032 | PJ-008 | Currency exposure on multi-year hardware commitment | Cost | 4 | 4 | Accept | L. Bergstrom | Open | 2026-09-25
RK-0033 | PJ-008 | Data adequacy ruling may require architecture rework | Regulatory | 3 | 4 | Avoid | L. Bergstrom | Monitoring | 2026-05-20
RK-0034 | PJ-009 | Chip allocation reduced by vendor under global demand | Supply Chain | 3 | 5 | Transfer | L. Bergstrom | Closed | 2026-12-11
RK-0035 | PJ-009 | Data adequacy ruling may require architecture rework | Regulatory | 2 | 5 | Transfer | L. Bergstrom | Open | 2026-06-14
RK-0036 | PJ-009 | Counterpart position may shift after national elections | Geopolitical | 3 | 1 | Avoid | L. Bergstrom | Open | 2027-03-04
RK-0037 | PJ-009 | Export licence approval slower than programme assumption | Geopolitical | 4 | 2 | Accept | L. Bergstrom | Open | 2026-12-18
RK-0038 | PJ-009 | Counterpart legal review extends beyond target signature | Schedule | 2 | 3 | Mitigate | L. Bergstrom | Monitoring | 2026-07-16
RK-0039 | PJ-011 | Sanctions regime change affects delivery route | Geopolitical | 2 | 2 | Accept | L. Bergstrom | Monitoring | 2027-04-17
RK-0040 | PJ-011 | Counterpart legal review extends beyond target signature | Schedule | 2 | 1 | Transfer | L. Bergstrom | Closed | 2026-09-24
RK-0041 | PJ-011 | Counterpart position may shift after national elections | Geopolitical | 2 | 4 | Avoid | L. Bergstrom | Closed | 2027-05-11
RK-0042 | PJ-011 | Chip allocation reduced by vendor under global demand | Supply Chain | 4 | 2 | Transfer | L. Bergstrom | Closed | 2026-10-26
RK-0043 | PJ-011 | Offset and local-content obligations not yet costed | Cost | 2 | 4 | Accept | L. Bergstrom | Monitoring | 2026-10-21
RK-0044 | PJ-012 | Offset and local-content obligations not yet costed | Cost | 4 | 4 | Accept | L. Bergstrom | Open | 2026-08-01
RK-0045 | PJ-012 | Chip allocation reduced by vendor under global demand | Supply Chain | 3 | 3 | Mitigate | L. Bergstrom | Open | 2026-08-05
RK-0046 | PJ-012 | Counterpart legal review extends beyond target signature | Schedule | 4 | 3 | Mitigate | L. Bergstrom | Open | 2026-08-01
RK-0047 | PJ-012 | Sanctions regime change affects delivery route | Geopolitical | 1 | 4 | Mitigate | L. Bergstrom | Monitoring | 2027-04-20
RK-0048 | PJ-012 | Counterpart position may shift after national elections | Geopolitical | 4 | 3 | Accept | L. Bergstrom | Monitoring | 2027-03-13
RK-0049 | PJ-012 | Export licence approval slower than programme assumption | Geopolitical | 2 | 2 | Mitigate | L. Bergstrom | Monitoring | 2026-06-02
RK-0050 | PJ-013 | Escalation in structural steel and copper pricing | Cost | 2 | 2 | Transfer | K. Duarte | Open | 2026-07-19
RK-0051 | PJ-013 | Water availability constraint at campus site | Environmental | 3 | 3 | Accept | K. Duarte | Open | 2026-05-28
RK-0052 | PJ-013 | Land handover contingent on unresolved zoning approval | Regulatory | 3 | 5 | Avoid | K. Duarte | Monitoring | 2026-09-24
RK-0053 | PJ-014 | Construction labour availability in peak season | Resource | 3 | 2 | Avoid | K. Duarte | Monitoring | 2027-06-09
RK-0054 | PJ-014 | Water availability constraint at campus site | Environmental | 1 | 2 | Mitigate | K. Duarte | Open | 2027-06-03
RK-0055 | PJ-014 | Grid connection date slips beyond facility readiness | Energy & Grid | 2 | 3 | Accept | K. Duarte | Open | 2026-06-12
RK-0056 | PJ-014 | Commissioning window collides with summer peak load | Schedule | 2 | 2 | Transfer | K. Duarte | Monitoring | 2026-10-01
RK-0057 | PJ-015 | Escalation in structural steel and copper pricing | Cost | 3 | 2 | Accept | K. Duarte | Closed | 2026-12-17
RK-0058 | PJ-015 | Transformer and switchgear lead times exceed 18 months | Supply Chain | 4 | 4 | Transfer | K. Duarte | Monitoring | 2027-02-11
RK-0059 | PJ-015 | Grid connection date slips beyond facility readiness | Energy & Grid | 5 | 4 | Transfer | K. Duarte | Open | 2026-07-19
RK-0060 | PJ-015 | Commissioning window collides with summer peak load | Schedule | 4 | 2 | Mitigate | K. Duarte | Open | 2026-12-31
RK-0061 | PJ-015 | Construction labour availability in peak season | Resource | 3 | 3 | Avoid | K. Duarte | Open | 2026-05-19
RK-0062 | PJ-015 | Cooling plant single-sourced with no qualified alternate | Supply Chain | 4 | 3 | Mitigate | K. Duarte | Closed | 2026-10-06
RK-0063 | PJ-016 | Escalation in structural steel and copper pricing | Cost | 3 | 3 | Mitigate | K. Duarte | Closed | 2026-07-14
RK-0064 | PJ-016 | Water availability constraint at campus site | Environmental | 5 | 3 | Avoid | K. Duarte | Open | 2026-06-28
RK-0065 | PJ-016 | Grid connection date slips beyond facility readiness | Energy & Grid | 4 | 3 | Mitigate | K. Duarte | Closed | 2027-02-21
RK-0066 | PJ-017 | Land handover contingent on unresolved zoning approval | Regulatory | 4 | 2 | Avoid | K. Duarte | Closed | 2026-08-16
RK-0067 | PJ-017 | Water availability constraint at campus site | Environmental | 3 | 3 | Accept | K. Duarte | Monitoring | 2026-10-24
RK-0068 | PJ-017 | Construction labour availability in peak season | Resource | 2 | 3 | Avoid | K. Duarte | Closed | 2026-08-05
RK-0069 | PJ-017 | Cooling plant single-sourced with no qualified alternate | Supply Chain | 1 | 1 | Avoid | K. Duarte | Closed | 2027-01-22
RK-0070 | PJ-017 | Escalation in structural steel and copper pricing | Cost | 2 | 2 | Mitigate | K. Duarte | Monitoring | 2027-05-04
RK-0071 | PJ-017 | Grid connection date slips beyond facility readiness | Energy & Grid | 2 | 4 | Mitigate | K. Duarte | Open | 2027-03-11
RK-0072 | PJ-018 | Land handover contingent on unresolved zoning approval | Regulatory | 3 | 4 | Accept | K. Duarte | Monitoring | 2026-11-02
RK-0073 | PJ-018 | Construction labour availability in peak season | Resource | 2 | 5 | Accept | K. Duarte | Monitoring | 2027-05-28
RK-0074 | PJ-019 | Cybersecurity accreditation not complete before go-live | Cyber | 2 | 5 | Avoid | T. Ivanova | Monitoring | 2027-04-27
RK-0075 | PJ-019 | Scarce ML platform talent attrition to private sector | Talent | 2 | 2 | Avoid | T. Ivanova | Open | 2026-11-23
RK-0076 | PJ-019 | Training run may not converge within allocated compute budget | Technical | 2 | 2 | Accept | T. Ivanova | Closed | 2026-07-03
RK-0077 | PJ-019 | Model evaluation standards not yet defined by regulator | Regulatory | 2 | 3 | Avoid | T. Ivanova | Closed | 2027-06-04
RK-0078 | PJ-019 | Benchmark performance unverified at production scale | Technical | 4 | 3 | Mitigate | T. Ivanova | Monitoring | 2027-01-11
RK-0079 | PJ-023 | Scarce ML platform talent attrition to private sector | Talent | 2 | 4 | Mitigate | T. Ivanova | Monitoring | 2026-06-21
RK-0080 | PJ-023 | Model evaluation standards not yet defined by regulator | Regulatory | 2 | 2 | Mitigate | T. Ivanova | Closed | 2027-01-10
RK-0081 | PJ-024 | Chip allocation reduced by vendor under global demand | Supply Chain | 2 | 4 | Transfer | H. Lindqvist | Open | 2027-05-13
RK-0082 | PJ-024 | Export licence approval slower than programme assumption | Geopolitical | 2 | 4 | Accept | H. Lindqvist | Open | 2026-08-10
RK-0083 | PJ-024 | Data adequacy ruling may require architecture rework | Regulatory | 3 | 2 | Avoid | H. Lindqvist | Monitoring | 2026-08-11
RK-0084 | PJ-024 | Counterpart position may shift after national elections | Geopolitical | 2 | 3 | Mitigate | H. Lindqvist | Open | 2027-03-16
RK-0085 | PJ-024 | Counterpart legal review extends beyond target signature | Schedule | 2 | 3 | Mitigate | H. Lindqvist | Open | 2026-10-03
RK-0086 | PJ-025 | Currency exposure on multi-year hardware commitment | Cost | 3 | 3 | Transfer | H. Lindqvist | Open | 2027-03-13
RK-0087 | PJ-025 | Counterpart legal review extends beyond target signature | Schedule | 2 | 2 | Mitigate | H. Lindqvist | Closed | 2026-10-16
RK-0088 | PJ-025 | Sanctions regime change affects delivery route | Geopolitical | 3 | 4 | Mitigate | H. Lindqvist | Open | 2026-10-02
RK-0089 | PJ-025 | Offset and local-content obligations not yet costed | Cost | 5 | 4 | Mitigate | H. Lindqvist | Closed | 2026-12-05
RK-0090 | PJ-025 | Chip allocation reduced by vendor under global demand | Supply Chain | 2 | 3 | Transfer | H. Lindqvist | Monitoring | 2027-02-24
RK-0091 | PJ-025 | Data adequacy ruling may require architecture rework | Regulatory | 3 | 4 | Avoid | H. Lindqvist | Open | 2027-05-01
RK-0092 | PJ-026 | Counterpart legal review extends beyond target signature | Schedule | 3 | 2 | Accept | H. Lindqvist | Open | 2026-06-17
RK-0093 | PJ-026 | Export licence approval slower than programme assumption | Geopolitical | 3 | 2 | Accept | H. Lindqvist | Open | 2026-05-21
RK-0094 | PJ-030 | Cooling plant single-sourced with no qualified alternate | Supply Chain | 2 | 2 | Mitigate | J. Alvarez | Open | 2026-10-18
RK-0095 | PJ-030 | Grid connection date slips beyond facility readiness | Energy & Grid | 3 | 3 | Transfer | J. Alvarez | Open | 2026-12-15
RK-0096 | PJ-030 | Water availability constraint at campus site | Environmental | 3 | 1 | Mitigate | J. Alvarez | Open | 2027-05-24
RK-0097 | PJ-030 | Transformer and switchgear lead times exceed 18 months | Supply Chain | 1 | 3 | Mitigate | J. Alvarez | Monitoring | 2027-03-08
RK-0098 | PJ-034 | Benchmark performance unverified at production scale | Technical | 4 | 2 | Accept | C. Nwosu | Monitoring | 2026-09-29
RK-0099 | PJ-034 | Training run may not converge within allocated compute budget | Technical | 3 | 2 | Transfer | C. Nwosu | Closed | 2027-03-25
RK-0100 | PJ-034 | Dependency on a single accelerator generation | Vendor | 3 | 3 | Accept | C. Nwosu | Open | 2026-05-24
RK-0101 | PJ-034 | Upstream data quality insufficient for target accuracy | Technical | 4 | 3 | Accept | C. Nwosu | Monitoring | 2026-12-17
RK-0102 | PJ-035 | Upstream data quality insufficient for target accuracy | Technical | 2 | 5 | Mitigate | C. Nwosu | Monitoring | 2027-02-27
RK-0103 | PJ-036 | Benchmark performance unverified at production scale | Technical | 5 | 3 | Accept | C. Nwosu | Open | 2026-08-28
RK-0104 | PJ-036 | Upstream data quality insufficient for target accuracy | Technical | 3 | 2 | Avoid | C. Nwosu | Open | 2026-07-02
RK-0105 | PJ-037 | Inference cost per token above commercial viability | Cost | 3 | 3 | Mitigate | C. Nwosu | Monitoring | 2026-08-10
RK-0106 | PJ-037 | Dependency on a single accelerator generation | Vendor | 2 | 2 | Avoid | C. Nwosu | Open | 2026-09-20
RK-0107 | PJ-038 | Inference cost per token above commercial viability | Cost | 2 | 1 | Avoid | C. Nwosu | Monitoring | 2027-06-09
RK-0108 | PJ-038 | Training run may not converge within allocated compute budget | Technical | 2 | 4 | Accept | C. Nwosu | Open | 2027-02-28
RK-0109 | PJ-038 | Upstream data quality insufficient for target accuracy | Technical | 4 | 2 | Transfer | C. Nwosu | Open | 2026-07-23
RK-0110 | PJ-038 | Scarce ML platform talent attrition to private sector | Talent | 3 | 3 | Accept | C. Nwosu | Open | 2027-05-26
RK-0111 | PJ-039 | Operating model for post-go-live support undefined | Resource | 3 | 3 | Accept | N. Haddad | Monitoring | 2027-04-01
RK-0112 | PJ-041 | Business availability for testing below plan | Resource | 3 | 2 | Accept | N. Haddad | Monitoring | 2027-02-24
RK-0113 | PJ-041 | Source system data access agreement unsigned | Regulatory | 4 | 2 | Avoid | N. Haddad | Open | 2026-06-24
RK-0114 | PJ-041 | Benefit assumptions untested with end users | Benefits | 1 | 3 | Accept | N. Haddad | Open | 2027-04-17
RK-0115 | PJ-041 | Operating model for post-go-live support undefined | Resource | 2 | 3 | Mitigate | N. Haddad | Closed | 2027-05-10
RK-0116 | PJ-042 | Sector regulator approval outstanding | Regulatory | 5 | 3 | Accept | N. Haddad | Open | 2027-03-31
RK-0117 | PJ-043 | Cybersecurity accreditation not complete before go-live | Cyber | 2 | 3 | Mitigate | N. Haddad | Open | 2026-11-09
RK-0118 | PJ-043 | Benchmark performance unverified at production scale | Technical | 2 | 3 | Avoid | N. Haddad | Monitoring | 2026-09-16
RK-0119 | PJ-044 | Benefit assumptions untested with end users | Benefits | 1 | 5 | Accept | N. Haddad | Monitoring | 2027-03-06
RK-0120 | PJ-044 | Sector regulator approval outstanding | Regulatory | 3 | 5 | Transfer | N. Haddad | Monitoring | 2026-07-21
RK-0121 | PJ-044 | Integration with legacy case system undocumented | Technical | 2 | 4 | Accept | N. Haddad | Open | 2026-05-26
RK-0122 | PJ-044 | Business availability for testing below plan | Resource | 1 | 3 | Transfer | N. Haddad | Monitoring | 2026-05-29
RK-0123 | PJ-045 | Operating model for post-go-live support undefined | Resource | 2 | 1 | Accept | Dr. F. Rossi | Monitoring | 2026-06-23
RK-0124 | PJ-046 | Cybersecurity accreditation not complete before go-live | Cyber | 4 | 2 | Accept | Dr. F. Rossi | Open | 2027-02-05
RK-0125 | PJ-046 | Inference cost per token above commercial viability | Cost | 2 | 1 | Accept | Dr. F. Rossi | Open | 2027-01-05
RK-0126 | PJ-046 | Model evaluation standards not yet defined by regulator | Regulatory | 3 | 4 | Mitigate | Dr. F. Rossi | Open | 2026-10-09
RK-0127 | PJ-047 | Benefit assumptions untested with end users | Benefits | 3 | 2 | Accept | Dr. F. Rossi | Open | 2026-11-13
RK-0128 | PJ-048 | Integration with legacy case system undocumented | Technical | 2 | 1 | Accept | Dr. F. Rossi | Open | 2027-03-25
RK-0129 | PJ-048 | Frontline adoption capacity constrained by change load | Change Adoption | 3 | 2 | Mitigate | Dr. F. Rossi | Open | 2026-08-28
RK-0130 | PJ-048 | Model bias review may require retraining | Regulatory | 1 | 2 | Accept | Dr. F. Rossi | Open | 2027-03-03
RK-0131 | PJ-049 | Operating model for post-go-live support undefined | Resource | 2 | 1 | Avoid | Dr. F. Rossi | Open | 2026-07-16
RK-0132 | PJ-049 | Integration with legacy case system undocumented | Technical | 3 | 5 | Mitigate | Dr. F. Rossi | Monitoring | 2026-10-28
RK-0133 | PJ-050 | Model bias review may require retraining | Regulatory | 3 | 4 | Avoid | G. Tanaka | Open | 2027-05-12
RK-0134 | PJ-050 | Business availability for testing below plan | Resource | 3 | 2 | Accept | G. Tanaka | Monitoring | 2026-07-09
RK-0135 | PJ-050 | Source system data access agreement unsigned | Regulatory | 3 | 2 | Transfer | G. Tanaka | Open | 2026-10-06
RK-0136 | PJ-050 | Operating model for post-go-live support undefined | Resource | 4 | 4 | Accept | G. Tanaka | Monitoring | 2027-01-18
RK-0137 | PJ-053 | Business availability for testing below plan | Resource | 4 | 2 | Transfer | G. Tanaka | Monitoring | 2027-05-27
RK-0138 | PJ-053 | Model bias review may require retraining | Regulatory | 2 | 4 | Mitigate | G. Tanaka | Closed | 2027-05-05
RK-0139 | PJ-054 | Source system data access agreement unsigned | Regulatory | 3 | 5 | Transfer | G. Tanaka | Open | 2026-09-16
RK-0140 | PJ-054 | Frontline adoption capacity constrained by change load | Change Adoption | 2 | 4 | Avoid | G. Tanaka | Monitoring | 2026-08-06
RK-0141 | PJ-056 | Model evaluation standards not yet defined by regulator | Regulatory | 1 | 2 | Transfer | R. Bhatt | Open | 2027-01-11
RK-0142 | PJ-056 | Training run may not converge within allocated compute budget | Technical | 3 | 4 | Accept | R. Bhatt | Monitoring | 2027-03-23
RK-0143 | PJ-056 | Cybersecurity accreditation not complete before go-live | Cyber | 2 | 4 | Accept | R. Bhatt | Open | 2027-04-01
RK-0144 | PJ-056 | Dependency on a single accelerator generation | Vendor | 3 | 4 | Accept | R. Bhatt | Open | 2026-07-27
RK-0145 | PJ-056 | Inference cost per token above commercial viability | Cost | 4 | 4 | Avoid | R. Bhatt | Open | 2026-05-26
RK-0146 | PJ-057 | Source system data access agreement unsigned | Regulatory | 2 | 3 | Avoid | R. Bhatt | Monitoring | 2026-06-28
RK-0147 | PJ-057 | Integration with legacy case system undocumented | Technical | 4 | 1 | Mitigate | R. Bhatt | Open | 2026-06-05
RK-0148 | PJ-057 | Sector regulator approval outstanding | Regulatory | 3 | 1 | Avoid | R. Bhatt | Monitoring | 2027-02-25
RK-0149 | PJ-057 | Operating model for post-go-live support undefined | Resource | 4 | 2 | Avoid | R. Bhatt | Open | 2026-06-08
RK-0150 | PJ-058 | Integration with legacy case system undocumented | Technical | 3 | 4 | Accept | R. Bhatt | Monitoring | 2026-11-05
RK-0151 | PJ-058 | Business availability for testing below plan | Resource | 2 | 3 | Accept | R. Bhatt | Open | 2027-05-13
RK-0152 | PJ-058 | Benefit assumptions untested with end users | Benefits | 5 | 1 | Avoid | R. Bhatt | Closed | 2027-05-07
RK-0153 | PJ-059 | Benefit assumptions untested with end users | Benefits | 2 | 2 | Transfer | R. Bhatt | Open | 2026-05-25
RK-0154 | PJ-059 | Source system data access agreement unsigned | Regulatory | 3 | 3 | Transfer | R. Bhatt | Open | 2027-02-07
RK-0155 | PJ-061 | Upstream data quality insufficient for target accuracy | Technical | 2 | 3 | Avoid | L. Moreau | Open | 2026-07-26
RK-0156 | PJ-061 | Inference cost per token above commercial viability | Cost | 3 | 3 | Transfer | L. Moreau | Open | 2026-12-27
RK-0157 | PJ-061 | Model evaluation standards not yet defined by regulator | Regulatory | 3 | 2 | Avoid | L. Moreau | Monitoring | 2026-09-07
RK-0158 | PJ-061 | Cybersecurity accreditation not complete before go-live | Cyber | 2 | 3 | Accept | L. Moreau | Closed | 2027-03-21
RK-0159 | PJ-062 | Integration with legacy case system undocumented | Technical | 4 | 3 | Accept | L. Moreau | Open | 2026-08-11
RK-0160 | PJ-062 | Frontline adoption capacity constrained by change load | Change Adoption | 3 | 2 | Avoid | L. Moreau | Open | 2026-09-02
RK-0161 | PJ-062 | Sector regulator approval outstanding | Regulatory | 1 | 1 | Transfer | L. Moreau | Open | 2027-05-25
RK-0162 | PJ-063 | Integration with legacy case system undocumented | Technical | 2 | 4 | Transfer | L. Moreau | Closed | 2027-05-17
RK-0163 | PJ-063 | Sector regulator approval outstanding | Regulatory | 2 | 3 | Accept | L. Moreau | Open | 2027-04-28
RK-0164 | PJ-063 | Business availability for testing below plan | Resource | 2 | 2 | Transfer | L. Moreau | Closed | 2026-12-22
RK-0165 | PJ-064 | Model evaluation standards not yet defined by regulator | Regulatory | 2 | 3 | Mitigate | I. Fernandes | Open | 2026-07-24
RK-0166 | PJ-064 | Upstream data quality insufficient for target accuracy | Technical | 3 | 2 | Avoid | I. Fernandes | Open | 2026-11-05
RK-0167 | PJ-064 | Cybersecurity accreditation not complete before go-live | Cyber | 1 | 3 | Avoid | I. Fernandes | Monitoring | 2027-04-27
RK-0168 | PJ-064 | Scarce ML platform talent attrition to private sector | Talent | 3 | 4 | Transfer | I. Fernandes | Open | 2026-07-14
RK-0169 | PJ-065 | Grid connection date slips beyond facility readiness | Energy & Grid | 2 | 3 | Accept | I. Fernandes | Closed | 2026-08-08
RK-0170 | PJ-065 | Construction labour availability in peak season | Resource | 2 | 1 | Transfer | I. Fernandes | Closed | 2026-08-06
RK-0171 | PJ-065 | Water availability constraint at campus site | Environmental | 2 | 5 | Accept | I. Fernandes | Open | 2027-01-23
RK-0172 | PJ-065 | Land handover contingent on unresolved zoning approval | Regulatory | 2 | 4 | Transfer | I. Fernandes | Monitoring | 2026-10-24
RK-0173 | PJ-066 | Benchmark performance unverified at production scale | Technical | 1 | 3 | Accept | I. Fernandes | Monitoring | 2027-01-07
RK-0174 | PJ-066 | Model evaluation standards not yet defined by regulator | Regulatory | 5 | 3 | Transfer | I. Fernandes | Monitoring | 2027-05-02
RK-0175 | PJ-066 | Training run may not converge within allocated compute budget | Technical | 3 | 2 | Accept | I. Fernandes | Closed | 2027-01-06
RK-0176 | PJ-067 | Frontline adoption capacity constrained by change load | Change Adoption | 2 | 3 | Mitigate | I. Fernandes | Open | 2027-05-30
RK-0177 | PJ-067 | Model bias review may require retraining | Regulatory | 3 | 3 | Transfer | I. Fernandes | Open | 2026-08-20
RK-0178 | PJ-067 | Source system data access agreement unsigned | Regulatory | 2 | 1 | Transfer | I. Fernandes | Closed | 2026-12-30
RK-0179 | PJ-068 | Cooling plant single-sourced with no qualified alternate | Supply Chain | 3 | 3 | Accept | M. Osei | Open | 2026-07-08
RK-0180 | PJ-068 | Commissioning window collides with summer peak load | Schedule | 3 | 3 | Avoid | M. Osei | Open | 2027-02-26
RK-0181 | PJ-068 | Land handover contingent on unresolved zoning approval | Regulatory | 2 | 3 | Accept | M. Osei | Open | 2027-05-13
RK-0182 | PJ-070 | Model evaluation standards not yet defined by regulator | Regulatory | 1 | 4 | Transfer | M. Osei | Open | 2026-06-13
RK-0183 | PJ-071 | Integration with legacy case system undocumented | Technical | 3 | 2 | Mitigate | M. Osei | Open | 2026-11-03
RK-0184 | PJ-073 | Benefit assumptions untested with end users | Benefits | 4 | 4 | Transfer | B. Okafor | Monitoring | 2027-03-10
RK-0185 | PJ-073 | Business availability for testing below plan | Resource | 4 | 4 | Avoid | B. Okafor | Closed | 2027-01-20
RK-0186 | PJ-073 | Frontline adoption capacity constrained by change load | Change Adoption | 2 | 2 | Accept | B. Okafor | Monitoring | 2027-01-04
RK-0187 | PJ-075 | Sector regulator approval outstanding | Regulatory | 4 | 1 | Avoid | B. Okafor | Open | 2026-11-21
RK-0188 | PJ-077 | Construction labour availability in peak season | Resource | 5 | 2 | Accept | D. Kaur | Open | 2027-04-26
RK-0189 | PJ-077 | Land handover contingent on unresolved zoning approval | Regulatory | 1 | 2 | Transfer | D. Kaur | Closed | 2026-09-18
RK-0190 | PJ-077 | Grid connection date slips beyond facility readiness | Energy & Grid | 4 | 4 | Transfer | D. Kaur | Closed | 2026-06-11
RK-0191 | PJ-077 | Commissioning window collides with summer peak load | Schedule | 4 | 1 | Accept | D. Kaur | Monitoring | 2026-06-21
RK-0192 | PJ-078 | Source system data access agreement unsigned | Regulatory | 1 | 4 | Avoid | D. Kaur | Monitoring | 2027-04-04
RK-0193 | PJ-080 | Operating model for post-go-live support undefined | Resource | 2 | 3 | Accept | D. Kaur | Open | 2027-04-17
RK-0194 | PJ-080 | Model bias review may require retraining | Regulatory | 1 | 3 | Mitigate | D. Kaur | Open | 2027-05-07
RK-0195 | PJ-080 | Source system data access agreement unsigned | Regulatory | 3 | 3 | Transfer | D. Kaur | Open | 2026-07-06
RK-0196 | PJ-080 | Frontline adoption capacity constrained by change load | Change Adoption | 4 | 2 | Avoid | D. Kaur | Open | 2027-01-02
RK-0197 | PJ-081 | Inference cost per token above commercial viability | Cost | 1 | 3 | Avoid | E. Castellani | Open | 2026-07-03
RK-0198 | PJ-081 | Model evaluation standards not yet defined by regulator | Regulatory | 5 | 4 | Accept | E. Castellani | Open | 2027-05-22
RK-0199 | PJ-081 | Cybersecurity accreditation not complete before go-live | Cyber | 2 | 2 | Transfer | E. Castellani | Open | 2026-11-25
RK-0200 | PJ-083 | Business availability for testing below plan | Resource | 4 | 3 | Avoid | E. Castellani | Open | 2027-05-23
RK-0201 | PJ-084 | Operating model for post-go-live support undefined | Resource | 2 | 2 | Mitigate | E. Castellani | Open | 2027-05-09
RK-0202 | PJ-084 | Sector regulator approval outstanding | Regulatory | 4 | 2 | Transfer | E. Castellani | Open | 2027-01-16
RK-0203 | PJ-084 | Integration with legacy case system undocumented | Technical | 1 | 4 | Mitigate | E. Castellani | Monitoring | 2027-02-17

## Issues
IssueID | ProjectID | IssueTitle | Severity | Owner | RaisedDate | TargetDate | Status
IS-0001 | PJ-001 | Contractor claim in dispute, blocking milestone certification | High | R. Nakamura | 2025-12-05 | 2026-01-03 | In Progress
IS-0002 | PJ-003 | Environment unavailable since the last platform release | Medium | R. Nakamura | 2026-01-12 | 2026-05-14 | Open
IS-0003 | PJ-004 | Interministerial approval overdue from sponsoring department | Medium | R. Nakamura | 2025-10-24 | 2026-02-22 | Resolved
IS-0004 | PJ-004 | Defect backlog above agreed exit criteria | High | R. Nakamura | 2026-02-01 | 2026-04-16 | Open
IS-0005 | PJ-004 | Vendor delivery slipped against contracted milestone | Low | R. Nakamura | 2026-07-09 | 2026-10-20 | In Progress
IS-0006 | PJ-007 | Vendor delivery slipped against contracted milestone | High | L. Bergstrom | 2025-11-26 | 2026-02-06 | Resolved
IS-0007 | PJ-008 | Environment unavailable since the last platform release | Medium | L. Bergstrom | 2025-12-23 | 2026-03-09 | Open
IS-0008 | PJ-008 | Defect backlog above agreed exit criteria | Medium | L. Bergstrom | 2026-02-03 | 2026-07-03 | Resolved
IS-0009 | PJ-008 | Vendor delivery slipped against contracted milestone | Medium | L. Bergstrom | 2026-02-04 | 2026-05-13 | In Progress
IS-0010 | PJ-008 | Key technical lead resigned from the delivery squad | Low | L. Bergstrom | 2026-02-16 | 2026-03-04 | Open
IS-0011 | PJ-009 | Vendor delivery slipped against contracted milestone | High | L. Bergstrom | 2025-12-26 | 2026-05-07 | Open
IS-0012 | PJ-009 | Site access delayed pending safety clearance | Medium | L. Bergstrom | 2026-06-01 | 2026-06-27 | In Progress
IS-0013 | PJ-009 | Defect backlog above agreed exit criteria | Medium | L. Bergstrom | 2026-05-01 | 2026-06-16 | Resolved
IS-0014 | PJ-009 | Interministerial approval overdue from sponsoring department | Medium | L. Bergstrom | 2026-03-18 | 2026-08-08 | In Progress
IS-0015 | PJ-011 | Defect backlog above agreed exit criteria | High | L. Bergstrom | 2026-08-15 | 2026-09-14 | Open
IS-0016 | PJ-011 | Interministerial approval overdue from sponsoring department | Medium | L. Bergstrom | 2026-01-13 | 2026-04-23 | In Progress
IS-0017 | PJ-011 | Site access delayed pending safety clearance | High | L. Bergstrom | 2026-07-23 | 2026-09-05 | Resolved
IS-0018 | PJ-011 | Accuracy benchmark not met in evaluation testing | High | L. Bergstrom | 2026-03-24 | 2026-05-16 | Resolved
IS-0019 | PJ-012 | Upstream dependency milestone missed by another programme | Medium | L. Bergstrom | 2026-01-01 | 2026-02-20 | Resolved
IS-0020 | PJ-012 | Data sharing agreement rejected by the source authority | Medium | L. Bergstrom | 2026-07-15 | 2026-12-07 | Resolved
IS-0021 | PJ-012 | Defect backlog above agreed exit criteria | Critical | L. Bergstrom | 2026-07-18 | 2026-09-18 | Open
IS-0022 | PJ-012 | Approved budget not yet released by treasury | Medium | L. Bergstrom | 2026-08-11 | 2026-10-24 | In Progress
IS-0023 | PJ-012 | Interministerial approval overdue from sponsoring department | High | L. Bergstrom | 2026-06-08 | 2026-07-29 | Resolved
IS-0024 | PJ-014 | Key technical lead resigned from the delivery squad | Critical | K. Duarte | 2025-11-14 | 2026-04-01 | Resolved
IS-0025 | PJ-017 | Counterpart has not confirmed the ratification timetable | Low | K. Duarte | 2025-11-07 | 2025-12-11 | Open
IS-0026 | PJ-017 | Scope change requested without an identified funding source | Low | K. Duarte | 2026-05-29 | 2026-10-24 | In Progress
IS-0027 | PJ-017 | Accuracy benchmark not met in evaluation testing | Medium | K. Duarte | 2026-04-14 | 2026-08-11 | Open
IS-0028 | PJ-017 | Interministerial approval overdue from sponsoring department | Medium | K. Duarte | 2026-07-18 | 2026-12-08 | In Progress
IS-0029 | PJ-017 | Vendor delivery slipped against contracted milestone | Medium | K. Duarte | 2026-05-11 | 2026-08-04 | In Progress
IS-0030 | PJ-018 | Key technical lead resigned from the delivery squad | Low | K. Duarte | 2026-08-01 | 2026-10-31 | Open
IS-0031 | PJ-018 | Vendor delivery slipped against contracted milestone | Low | K. Duarte | 2026-01-01 | 2026-04-06 | In Progress
IS-0032 | PJ-018 | Defect backlog above agreed exit criteria | Medium | K. Duarte | 2025-11-18 | 2026-02-20 | Open
IS-0033 | PJ-018 | Accuracy benchmark not met in evaluation testing | High | K. Duarte | 2025-11-01 | 2025-12-07 | In Progress
IS-0034 | PJ-019 | Data sharing agreement rejected by the source authority | Low | T. Ivanova | 2025-11-03 | 2026-03-15 | In Progress
IS-0035 | PJ-019 | Approved budget not yet released by treasury | Medium | T. Ivanova | 2026-05-26 | 2026-08-07 | In Progress
IS-0036 | PJ-023 | Upstream dependency milestone missed by another programme | Critical | T. Ivanova | 2026-03-03 | 2026-03-17 | Resolved
IS-0037 | PJ-023 | Site access delayed pending safety clearance | Medium | T. Ivanova | 2026-05-15 | 2026-06-17 | Open
IS-0038 | PJ-023 | Scope change requested without an identified funding source | High | T. Ivanova | 2026-02-05 | 2026-06-01 | Open
IS-0039 | PJ-023 | Key technical lead resigned from the delivery squad | Medium | T. Ivanova | 2026-05-16 | 2026-06-03 | Open
IS-0040 | PJ-023 | Approved budget not yet released by treasury | Critical | T. Ivanova | 2026-06-25 | 2026-07-13 | Resolved
IS-0041 | PJ-024 | Site access delayed pending safety clearance | High | H. Lindqvist | 2025-10-30 | 2026-02-05 | In Progress
IS-0042 | PJ-024 | Approved budget not yet released by treasury | Low | H. Lindqvist | 2025-11-12 | 2026-02-03 | Resolved
IS-0043 | PJ-024 | Counterpart has not confirmed the ratification timetable | High | H. Lindqvist | 2025-11-12 | 2025-12-19 | In Progress
IS-0044 | PJ-024 | Environment unavailable since the last platform release | Medium | H. Lindqvist | 2025-12-26 | 2026-01-17 | Open
IS-0045 | PJ-026 | Contractor claim in dispute, blocking milestone certification | Medium | H. Lindqvist | 2026-04-07 | 2026-07-10 | In Progress
IS-0046 | PJ-026 | Environment unavailable since the last platform release | Medium | H. Lindqvist | 2026-05-28 | 2026-10-01 | Open
IS-0047 | PJ-026 | Key technical lead resigned from the delivery squad | Medium | H. Lindqvist | 2026-04-09 | 2026-05-05 | In Progress
IS-0048 | PJ-030 | Accuracy benchmark not met in evaluation testing | Critical | J. Alvarez | 2026-01-16 | 2026-03-18 | In Progress
IS-0049 | PJ-030 | Upstream dependency milestone missed by another programme | High | J. Alvarez | 2026-01-14 | 2026-05-27 | Resolved
IS-0050 | PJ-030 | Approved budget not yet released by treasury | Medium | J. Alvarez | 2026-04-19 | 2026-06-22 | In Progress
IS-0051 | PJ-030 | Contractor claim in dispute, blocking milestone certification | Medium | J. Alvarez | 2026-06-26 | 2026-09-02 | In Progress
IS-0052 | PJ-030 | Key technical lead resigned from the delivery squad | Medium | J. Alvarez | 2026-07-03 | 2026-08-27 | In Progress
IS-0053 | PJ-036 | Accuracy benchmark not met in evaluation testing | Medium | C. Nwosu | 2026-01-06 | 2026-02-16 | Open
IS-0054 | PJ-037 | Upstream dependency milestone missed by another programme | High | C. Nwosu | 2026-02-12 | 2026-05-07 | Open
IS-0055 | PJ-037 | Scope change requested without an identified funding source | Medium | C. Nwosu | 2025-11-19 | 2026-04-05 | Resolved
IS-0056 | PJ-037 | Security review raised findings blocking accreditation | Low | C. Nwosu | 2026-08-07 | 2026-09-11 | Resolved
IS-0057 | PJ-037 | Interministerial approval overdue from sponsoring department | Critical | C. Nwosu | 2026-03-19 | 2026-07-10 | In Progress
IS-0058 | PJ-038 | Interministerial approval overdue from sponsoring department | Medium | C. Nwosu | 2026-06-09 | 2026-07-23 | Resolved
IS-0059 | PJ-038 | Accuracy benchmark not met in evaluation testing | High | C. Nwosu | 2025-12-19 | 2026-04-30 | Open
IS-0060 | PJ-038 | Environment unavailable since the last platform release | High | C. Nwosu | 2026-02-10 | 2026-06-16 | Open
IS-0061 | PJ-041 | Counterpart has not confirmed the ratification timetable | Medium | N. Haddad | 2025-12-18 | 2026-03-07 | Open
IS-0062 | PJ-042 | Contractor claim in dispute, blocking milestone certification | Medium | N. Haddad | 2026-05-22 | 2026-06-13 | Open
IS-0063 | PJ-042 | Scope change requested without an identified funding source | Critical | N. Haddad | 2026-03-28 | 2026-08-11 | Resolved
IS-0064 | PJ-042 | Site access delayed pending safety clearance | Low | N. Haddad | 2026-07-09 | 2026-07-26 | Resolved
IS-0065 | PJ-043 | Vendor delivery slipped against contracted milestone | Low | N. Haddad | 2026-05-17 | 2026-08-09 | Open
IS-0066 | PJ-043 | Environment unavailable since the last platform release | Critical | N. Haddad | 2026-08-02 | 2026-10-30 | Open
IS-0067 | PJ-043 | Contractor claim in dispute, blocking milestone certification | Low | N. Haddad | 2026-06-15 | 2026-09-02 | Open
IS-0068 | PJ-043 | Approved budget not yet released by treasury | Medium | N. Haddad | 2025-11-05 | 2025-12-25 | Resolved
IS-0069 | PJ-043 | Defect backlog above agreed exit criteria | High | N. Haddad | 2026-06-03 | 2026-09-30 | In Progress
IS-0070 | PJ-044 | Vendor delivery slipped against contracted milestone | Medium | N. Haddad | 2026-08-02 | 2026-11-06 | Open
IS-0071 | PJ-044 | Defect backlog above agreed exit criteria | Low | N. Haddad | 2026-05-08 | 2026-08-21 | In Progress
IS-0072 | PJ-045 | Security review raised findings blocking accreditation | Low | Dr. F. Rossi | 2026-04-21 | 2026-06-29 | In Progress
IS-0073 | PJ-045 | Contractor claim in dispute, blocking milestone certification | Critical | Dr. F. Rossi | 2025-11-13 | 2026-03-04 | In Progress
IS-0074 | PJ-046 | Interministerial approval overdue from sponsoring department | Medium | Dr. F. Rossi | 2026-06-05 | 2026-08-09 | Resolved
IS-0075 | PJ-046 | Security review raised findings blocking accreditation | Medium | Dr. F. Rossi | 2026-02-17 | 2026-04-30 | In Progress
IS-0076 | PJ-046 | Site access delayed pending safety clearance | Low | Dr. F. Rossi | 2026-05-21 | 2026-07-23 | In Progress
IS-0077 | PJ-047 | Approved budget not yet released by treasury | Medium | Dr. F. Rossi | 2026-03-21 | 2026-04-26 | Resolved
IS-0078 | PJ-047 | Data sharing agreement rejected by the source authority | Low | Dr. F. Rossi | 2026-01-06 | 2026-05-27 | Resolved
IS-0079 | PJ-047 | Vendor delivery slipped against contracted milestone | Medium | Dr. F. Rossi | 2025-12-11 | 2026-04-19 | Resolved
IS-0080 | PJ-050 | Interministerial approval overdue from sponsoring department | High | G. Tanaka | 2026-04-10 | 2026-05-07 | In Progress
IS-0081 | PJ-050 | Security review raised findings blocking accreditation | Medium | G. Tanaka | 2026-03-04 | 2026-04-10 | Open
IS-0082 | PJ-051 | Contractor claim in dispute, blocking milestone certification | High | G. Tanaka | 2025-11-15 | 2026-04-10 | Resolved
IS-0083 | PJ-051 | Site access delayed pending safety clearance | Medium | G. Tanaka | 2026-04-26 | 2026-06-24 | Open
IS-0084 | PJ-051 | Accuracy benchmark not met in evaluation testing | Medium | G. Tanaka | 2026-01-21 | 2026-04-11 | Open
IS-0085 | PJ-053 | Approved budget not yet released by treasury | Medium | G. Tanaka | 2026-05-13 | 2026-06-23 | Resolved
IS-0086 | PJ-053 | Vendor delivery slipped against contracted milestone | Critical | G. Tanaka | 2026-07-09 | 2026-07-29 | Open
IS-0087 | PJ-053 | Key technical lead resigned from the delivery squad | Medium | G. Tanaka | 2026-01-17 | 2026-06-08 | Resolved
IS-0088 | PJ-055 | Approved budget not yet released by treasury | Low | R. Bhatt | 2026-06-15 | 2026-07-25 | Open
IS-0089 | PJ-055 | Contractor claim in dispute, blocking milestone certification | Medium | R. Bhatt | 2026-01-19 | 2026-04-08 | Open
IS-0090 | PJ-055 | Environment unavailable since the last platform release | Medium | R. Bhatt | 2026-04-29 | 2026-08-06 | Resolved
IS-0091 | PJ-055 | Defect backlog above agreed exit criteria | Medium | R. Bhatt | 2026-05-15 | 2026-08-01 | Open
IS-0092 | PJ-057 | Counterpart has not confirmed the ratification timetable | Medium | R. Bhatt | 2026-05-01 | 2026-07-21 | In Progress
IS-0093 | PJ-058 | Environment unavailable since the last platform release | High | R. Bhatt | 2025-12-05 | 2026-02-05 | Open
IS-0094 | PJ-058 | Data sharing agreement rejected by the source authority | High | R. Bhatt | 2026-02-10 | 2026-07-08 | Open
IS-0095 | PJ-058 | Defect backlog above agreed exit criteria | Medium | R. Bhatt | 2026-04-30 | 2026-07-02 | Open
IS-0096 | PJ-058 | Scope change requested without an identified funding source | High | R. Bhatt | 2025-12-03 | 2026-04-01 | Open
IS-0097 | PJ-059 | Data sharing agreement rejected by the source authority | High | R. Bhatt | 2026-03-08 | 2026-04-28 | In Progress
IS-0098 | PJ-059 | Vendor delivery slipped against contracted milestone | High | R. Bhatt | 2026-03-28 | 2026-08-07 | Resolved
IS-0099 | PJ-059 | Interministerial approval overdue from sponsoring department | Low | R. Bhatt | 2026-03-10 | 2026-05-15 | Open
IS-0100 | PJ-059 | Scope change requested without an identified funding source | High | R. Bhatt | 2026-04-16 | 2026-05-08 | Open
IS-0101 | PJ-059 | Contractor claim in dispute, blocking milestone certification | Medium | R. Bhatt | 2026-03-01 | 2026-06-14 | Open
IS-0102 | PJ-060 | Counterpart has not confirmed the ratification timetable | Medium | L. Moreau | 2025-12-19 | 2026-02-14 | Open
IS-0103 | PJ-060 | Approved budget not yet released by treasury | Low | L. Moreau | 2026-06-10 | 2026-08-17 | In Progress
IS-0104 | PJ-060 | Data sharing agreement rejected by the source authority | High | L. Moreau | 2026-08-04 | 2026-12-22 | Resolved
IS-0105 | PJ-060 | Accuracy benchmark not met in evaluation testing | High | L. Moreau | 2025-12-25 | 2026-02-02 | In Progress
IS-0106 | PJ-060 | Key technical lead resigned from the delivery squad | Low | L. Moreau | 2026-02-07 | 2026-06-13 | In Progress
IS-0107 | PJ-061 | Environment unavailable since the last platform release | Medium | L. Moreau | 2025-10-28 | 2026-01-20 | In Progress
IS-0108 | PJ-061 | Data sharing agreement rejected by the source authority | Low | L. Moreau | 2026-03-27 | 2026-08-22 | In Progress
IS-0109 | PJ-061 | Accuracy benchmark not met in evaluation testing | Low | L. Moreau | 2026-05-02 | 2026-06-24 | In Progress
IS-0110 | PJ-061 | Upstream dependency milestone missed by another programme | High | L. Moreau | 2026-06-18 | 2026-09-07 | Resolved
IS-0111 | PJ-063 | Security review raised findings blocking accreditation | Low | L. Moreau | 2026-03-09 | 2026-08-04 | Open
IS-0112 | PJ-063 | Upstream dependency milestone missed by another programme | High | L. Moreau | 2026-01-14 | 2026-02-09 | Resolved
IS-0113 | PJ-064 | Environment unavailable since the last platform release | Medium | I. Fernandes | 2026-05-19 | 2026-07-09 | Open
IS-0114 | PJ-064 | Key technical lead resigned from the delivery squad | Low | I. Fernandes | 2026-02-21 | 2026-04-07 | In Progress
IS-0115 | PJ-064 | Scope change requested without an identified funding source | Medium | I. Fernandes | 2025-12-14 | 2026-05-07 | In Progress
IS-0116 | PJ-065 | Accuracy benchmark not met in evaluation testing | Medium | I. Fernandes | 2025-11-08 | 2026-03-11 | Open
IS-0117 | PJ-065 | Interministerial approval overdue from sponsoring department | High | I. Fernandes | 2026-03-02 | 2026-05-05 | Open
IS-0118 | PJ-065 | Contractor claim in dispute, blocking milestone certification | Low | I. Fernandes | 2026-03-23 | 2026-04-25 | In Progress
IS-0119 | PJ-065 | Vendor delivery slipped against contracted milestone | Medium | I. Fernandes | 2025-10-30 | 2026-01-11 | Open
IS-0120 | PJ-067 | Key technical lead resigned from the delivery squad | Critical | I. Fernandes | 2026-01-27 | 2026-04-27 | In Progress
IS-0121 | PJ-067 | Upstream dependency milestone missed by another programme | Medium | I. Fernandes | 2025-12-24 | 2026-03-23 | Open
IS-0122 | PJ-067 | Counterpart has not confirmed the ratification timetable | Medium | I. Fernandes | 2026-07-10 | 2026-10-24 | In Progress
IS-0123 | PJ-069 | Upstream dependency milestone missed by another programme | Medium | M. Osei | 2026-04-08 | 2026-08-29 | Open
IS-0124 | PJ-069 | Environment unavailable since the last platform release | Medium | M. Osei | 2026-05-14 | 2026-09-16 | Open
IS-0125 | PJ-069 | Interministerial approval overdue from sponsoring department | Medium | M. Osei | 2026-05-10 | 2026-07-26 | Open
IS-0126 | PJ-069 | Key technical lead resigned from the delivery squad | Low | M. Osei | 2026-04-28 | 2026-05-31 | Open
IS-0127 | PJ-071 | Upstream dependency milestone missed by another programme | Medium | M. Osei | 2025-11-08 | 2026-03-08 | Resolved
IS-0128 | PJ-073 | Approved budget not yet released by treasury | Low | B. Okafor | 2026-01-17 | 2026-02-20 | Open
IS-0129 | PJ-073 | Defect backlog above agreed exit criteria | High | B. Okafor | 2025-12-31 | 2026-04-28 | Open
IS-0130 | PJ-075 | Site access delayed pending safety clearance | High | B. Okafor | 2026-05-01 | 2026-08-20 | In Progress
IS-0131 | PJ-075 | Contractor claim in dispute, blocking milestone certification | Medium | B. Okafor | 2026-07-04 | 2026-07-27 | In Progress
IS-0132 | PJ-075 | Vendor delivery slipped against contracted milestone | Medium | B. Okafor | 2026-01-10 | 2026-02-06 | In Progress
IS-0133 | PJ-075 | Accuracy benchmark not met in evaluation testing | Medium | B. Okafor | 2026-05-17 | 2026-06-03 | Open
IS-0134 | PJ-077 | Upstream dependency milestone missed by another programme | High | D. Kaur | 2026-04-26 | 2026-09-08 | Resolved
IS-0135 | PJ-077 | Data sharing agreement rejected by the source authority | High | D. Kaur | 2025-11-30 | 2026-02-02 | Resolved
IS-0136 | PJ-077 | Counterpart has not confirmed the ratification timetable | Low | D. Kaur | 2025-11-19 | 2026-03-08 | In Progress
IS-0137 | PJ-078 | Data sharing agreement rejected by the source authority | Medium | D. Kaur | 2026-03-25 | 2026-07-08 | Open
IS-0138 | PJ-081 | Security review raised findings blocking accreditation | Medium | E. Castellani | 2025-12-28 | 2026-03-12 | In Progress
IS-0139 | PJ-083 | Data sharing agreement rejected by the source authority | Medium | E. Castellani | 2026-02-20 | 2026-04-07 | Resolved
IS-0140 | PJ-084 | Vendor delivery slipped against contracted milestone | Critical | E. Castellani | 2026-05-24 | 2026-09-17 | Open

## LessonsLearned
LessonID | ProjectID | Category | Lesson | Recommendation | DateCaptured
LL-0001 | PJ-001 | Quality | Contingency was consumed before the executing phase began | Hold contingency at portfolio level and release it by exception | 2025-07-11
LL-0002 | PJ-001 | Planning | Sector regulator was engaged only at pilot stage | Bring the regulator into design review for any citizen-facing model | 2026-01-27
LL-0003 | PJ-001 | Governance | Model evaluation criteria were agreed after training had started | Fix evaluation and red-team criteria before the first training run | 2026-07-22
LL-0004 | PJ-008 | Communication | Export licence dependency surfaced only at contract signature | Run an export-control assessment during business case, not after | 2025-08-13
LL-0005 | PJ-008 | Procurement | Change network stood up too late for frontline adoption | Appoint change leads at the same time as the project manager | 2025-09-13
LL-0006 | PJ-008 | Procurement | Model evaluation criteria were agreed after training had started | Fix evaluation and red-team criteria before the first training run | 2025-10-31
LL-0007 | PJ-009 | Communication | Grid connection lead time was assumed, not confirmed with the utility | Make a written utility connection date a gate condition before capital release | 2025-08-29
LL-0008 | PJ-009 | Planning | Model evaluation criteria were agreed after training had started | Fix evaluation and red-team criteria before the first training run | 2025-11-22
LL-0009 | PJ-009 | Stakeholder | Benefit telemetry was not instrumented at go-live | Make benefit measurement a mandatory acceptance criterion | 2026-07-02
LL-0010 | PJ-011 | Risk | Bilateral agreement lacked an agreed dispute mechanism | Require a dispute and exit clause in every G2G term sheet | 2026-03-03
LL-0011 | PJ-011 | Procurement | Sector regulator was engaged only at pilot stage | Bring the regulator into design review for any citizen-facing model | 2026-07-16
LL-0012 | PJ-014 | Communication | Grid connection lead time was assumed, not confirmed with the utility | Make a written utility connection date a gate condition before capital release | 2025-11-03
LL-0013 | PJ-030 | Governance | Compute was procured before the workload profile was understood | Baseline the workload mix before committing to accelerator generation | 2025-12-19
LL-0014 | PJ-034 | Governance | Sector regulator was engaged only at pilot stage | Bring the regulator into design review for any citizen-facing model | 2026-01-04
LL-0015 | PJ-034 | Resource | Benefit telemetry was not instrumented at go-live | Make benefit measurement a mandatory acceptance criterion | 2026-01-04
LL-0016 | PJ-055 | Stakeholder | Contingency was consumed before the executing phase began | Hold contingency at portfolio level and release it by exception | 2025-11-10
LL-0017 | PJ-057 | Procurement | Bilateral agreement lacked an agreed dispute mechanism | Require a dispute and exit clause in every G2G term sheet | 2026-04-03
LL-0018 | PJ-060 | Planning | Bilateral agreement lacked an agreed dispute mechanism | Require a dispute and exit clause in every G2G term sheet | 2025-08-21
LL-0019 | PJ-060 | Quality | Three departments built overlapping document AI capability | Route all sector use cases through a central capability register first | 2026-03-31
LL-0020 | PJ-060 | Planning | Export licence dependency surfaced only at contract signature | Run an export-control assessment during business case, not after | 2026-04-08
LL-0021 | PJ-067 | Procurement | Bilateral agreement lacked an agreed dispute mechanism | Require a dispute and exit clause in every G2G term sheet | 2026-04-04
LL-0022 | PJ-067 | Communication | Sector regulator was engaged only at pilot stage | Bring the regulator into design review for any citizen-facing model | 2026-06-04
LL-0023 | PJ-071 | Stakeholder | Bilateral agreement lacked an agreed dispute mechanism | Require a dispute and exit clause in every G2G term sheet | 2025-10-28
LL-0024 | PJ-071 | Procurement | Model evaluation criteria were agreed after training had started | Fix evaluation and red-team criteria before the first training run | 2026-04-28
LL-0025 | PJ-073 | Procurement | Benefit telemetry was not instrumented at go-live | Make benefit measurement a mandatory acceptance criterion | 2026-07-11
LL-0026 | PJ-073 | Quality | Change network stood up too late for frontline adoption | Appoint change leads at the same time as the project manager | 2026-06-18
LL-0027 | PJ-073 | Procurement | Three departments built overlapping document AI capability | Route all sector use cases through a central capability register first | 2026-01-09
LL-0028 | PJ-075 | Planning | Benefit telemetry was not instrumented at go-live | Make benefit measurement a mandatory acceptance criterion | 2025-08-31
LL-0029 | PJ-075 | Governance | Change network stood up too late for frontline adoption | Appoint change leads at the same time as the project manager | 2026-05-18
LL-0030 | PJ-077 | Resource | Contingency was consumed before the executing phase began | Hold contingency at portfolio level and release it by exception | 2026-01-03
LL-0031 | PJ-077 | Planning | Grid connection lead time was assumed, not confirmed with the utility | Make a written utility connection date a gate condition before capital release | 2026-02-03

## Config
Setting | Value | Notes
CPI_Green | 0.95 | Cost Performance Index at or above this = Green
CPI_Amber | 0.85 | CPI at or above this (below Green) = Amber; below = Red
SPI_Green | 0.95 | Schedule Performance Index at or above this = Green
SPI_Amber | 0.85 | SPI at or above this (below Green) = Amber; below = Red
Risk_Green | 10 | Highest open risk exposure (Probability x Impact) at or below this = Green
Risk_Amber | 16 | Highest open risk exposure at or below this = Amber; above = Red (so Red needs high probability AND high impact)
Rollup_RiskRed_Share | 0.2
Rollup_RiskAmber_Share | 0.08
Rollup_DeliveryRed_Share | 0.3
Rollup_DeliveryAmber_Share | 0.15
Currency | USD | Reporting currency for all monetary values
ReportingDate | 2026-08-16 | As-at date for elapsed and overdue calculations